Lancashire's Vision

We will deliver the outcomes in the plan in partnership through an understanding of the lived experience of a child or young person by:

- Delivering the right service, at the right time, by the right people through effective wellbeing and preventative strategies.

- Purposeful and effective social work and care intervention, engaging children, young people and families by building on their strengths.

- Focusing on permanence, by delivering lasting and sustainable outcomes for children, young people and their families.

Introduction

Our services for children have improved significantly.  Our 2015 Ofsted inspection rated the overall service provision to be inadequate.  In 2018 the judgement was that services were no longer inadequate, but require improvement to be good. Our Adoption Service was judged to be good.  Ofsted found that staff were positive, open to learning and committed to their work with children and families.  The service knows itself well and appropriate action was in place to improve services and that multi-agency strategic partnerships are stronger leading to a more shared approach.

There is still more to do to ensure that all children receive a consistently good service. In total, Ofsted made 11 recommendations in which we need to continue to strengthen and improve practice. They are categorised in six key areas:

| Effective Partnership Working Lead: Sally Allen | We will ensure effective, collaborative partnership arrangements are in place which support the improvement of services to children and families. Specifically, with partners we will improve our response to children living with domestic abuse and neglect, ensuring services are focused on delivering effective, preventative and targeted support. |
| --- | --- |
| Prevention Lead: Debbie Duffell | We will work with partners to ensure that an effective range of early help services are in place to support children and families when they first need help. We will continue to develop the Multi-Agency Safeguarding Hub (MASH) to ensure continued effective decision making and service provision at the front door. |
| Purposeful Practice Lead: Bertie Goffe | We will ensure that everything we do makes a tangible, positive difference to the lives of the children we work for and that we intervene at the lowest and least intrusive level possible. We will improve the quality of assessments and plans and spell out for families what needs to change and how this is likely to be achieved. We will also strengthen the critical challenge of first line managers and Independent Reviewing Officers to prevent drift and delay. |
| Permanence and Children in Our Care Lead: Barbara Bath Stephen Belbin | We will work tirelessly with families to prevent the need for children to become looked after. Where children are not able to live safely with their family, we will ensure that plans for permanence are developed at the earliest opportunity. We will ensure care plans are more rigorously monitored and reviewed to reduce drift and delay, including the timely revocation of Care Orders where children have been successfully returned home. We want all our children to meet their potential. We will strive to improve educational attainment and health outcomes and will specifically focus on improving the educational attainment and progress of children looked after (CLA) at Key Stage 4. We want all our children that leave care to live healthy, successful, fulfilling lives. We will ensure that all our care leavers receive timely and accessible support to meet their financial, educational and emotional health needs. |
| Effective Use of Performance Data Lead: Brendan Lee | Whilst significant progress has been made in improving the accuracy of performance data, we need to improve the use of data so that it is an effective tool to help managers measure progress and examine trends. |
| Workforce Development Lead: Victoria Gent | We want our children and families to benefit from a sufficient, stable, suitably qualified and competent workforce. We recognise that our staff are our most valuable resource and we will continue to invest heavily in their development and progression. We need to consistently strengthen our retention of permanent staff across the county. We will build our training offer for social workers, support workers and managers, ensuring this is aligned to priority areas of development. |

| Ofsted Inspection Report Recommendations (August 2018) | Key Area |
| --- | --- |
| 1. | Work with partners to ensure that an effective range of early help services is in place to support children and families when they first need help. | Prevention |
| 2. | Ensure that assessments clearly articulate risks and protective factors, provide robust analysis and spell out what needs to change and how that is likely to be achieved. | Purposeful Practice |
| 3. | Ensure that all plans for children in need, children subject to child protection plans, looked after children and care leavers are specific, measureable and outcome-focused. | Purposeful Practice |
| 4. | Ensure that the quality of critical challenge provided by first line managers, IROs in looked after reviews and conference chairs within child protection conferences are effective in avoiding drift and delay. | Purposeful Practice |
| 5. | Ensure that the local authority and partners share a common understanding of the risks associated with neglect, in all its different forms, and have the tools they need to monitor and measure their impact in managing change. | Effective Partnership Working |
| 6. | Improve the educational attainment and progress of children looked after at Key Stage 4. | Permanence and Children in our Care |
| 7. | Ensure that permanence planning, including for those children who return home, is rigorously monitored and reviewed on a consistent basis across the county to reduce the likelihood of drift and delay. | Permanence and Children in our Care |
| 8. | Ensure that when children successfully return home, timely revocation hearings are held to secure permanence plans for them to remain in the care of their parents. | Permanence and Children in our Care |
| 9. | Ensure that care leavers receive timely and accessible support that meets their financial, educational and emotional health needs. | Permanence and Children in our Care |
| 10. | Improve the use of performance data so that it is an effective tool to help managers measure progress and examine trends. | Effective Use of Performance Data |
| 11. | Work with partners to ensure that responses for children and families living with domestic abuse are focused on delivering effective, preventative and targeted support. | Effective Partnership Working |

Implementing the Improvement Plan

This plan focuses on the actions required to deliver the Ofsted recommendations and other key priorities identified in our self-assessment, with the aim of securing improvement and delivering consistently good services for Lancashire's children, young people and families.

The plan sets out the actions that will be undertaken, the expected outcomes, improvement measures, lead officers, targets and due dates. More detailed action plans, led by specific Delivery Boards, will drive specific service improvement (see Appendix 1). Sitting alongside this document is our Purposeful Practice Framework and our Corporate Parenting Strategy. It is also part of a number of strategies and plans that fit together to deliver improvement for children (see Appendix 2).  The plan will be overseen by the Lancashire Getting to Good Board which will meet six weekly to review progress.

Each outcome will be RAG rated, as part of our monitoring arrangements, with the status descriptions detailed below:

| RAG Table | Status |
| --- | --- |
| RED | Tasks and or outcomes have not been met or the timescale has slipped. |
| AMBER | Tasks and outcomes are on track, milestones met, but full action(s) have not been completed. |
| GREEN | Tasks and outcomes or performance is on target. |
| BLUE | Completed. |

| Key Area 1: Effective Partnership Working Lead: Sally Allen |
| --- |
| Outcome statements: Effective, collaborative partnership working arrangements are in place which support the improvement of services to children and families. Children who experience neglect have their needs identified and effectively managed. Children who experience domestic abuse receive timely and appropriate support that meets their needs. |
|  | Action | Ofsted Ref | Due | Lead |
| 1.1 | Lead the development of effective collaborative partnership strategies and plans which support the improvement of services to children and families |
| 1.1.1 | Establish a multi-agency strategic governance board, with strategic responsibility and accountability for the children's agenda. | Recommendation 1,5,6,8,11 | November 2018 | Edwina Grant OBE Executive Director of Education and Children's Services |
| 1.1.2 | Implement a co-produced strategy and action plan to improve education outcomes for children & young people (CYP) with SEND. | Recommendation 1 | June 2019 | Stephen Belbin Local Authority Head of Education, Quality and Performance |
| 1.2 | Embed an agreed approach to effectively identifying and managing neglect |
| 1.2.1 | Develop a refreshed multi-agency Neglect Strategy in consultation with a wide range of partners. | Recommendation 5 | March 2019 | Victoria Gent Head of Service, CSC, East Locality Jane Booth Chair of Lancashire Safeguarding Children Board (LSCB) |
| 1.2.2 | Develop operational delivery plans to ensure effective and meaningful delivery of the updated strategy. | Recommendation 5 | April 2019 | Victoria Gent Head of Service CSC, East Locality Jane Booth Chair of LSCB |
| 1.2.3 | Deliver refreshed training to support the delivery of the Neglect Strategy. | Recommendation 5 | June 2019 | Victoria Gent Head of Service, CSC, East Locality Chair of LSCB |
| 1.2.4 | Develop an online toolkit to support the delivery of the Neglect Strategy. | Recommendation 5 | May 2019 | Victoria Gent Head of Service CSC, East Locality Jane Booth Chair of LSCB |
| 1.2.5 | Monitor and measure the impact of the Neglect Strategy and delivery plans. | Recommendation 5 | October 2019 | Victoria Gent Head of Service CSC, East Locality Jane Booth Chair of LSCB |
| 1.3 | Ensure that effective, preventative and targeted support is in place for children and families living with domestic abuse |
| 1.3.1 | Review the multi-agency response to domestic abuse, to ensure effective, preventative and targeted support pathways are in place for children and families. | Recommendation 11 | May 2019 | Brendan Lee Head of Service CSC, North Locality |
| 1.3.2 | Develop and deliver a workforce development programme and work place policy to improve understanding of the impact of domestic abuse on children and to develop purposeful practice in this area. | Recommendation 11 | May 2019 | Brendan Lee Head of Service CSC, North Locality |
| 1.3.3 | Develop and deliver a workplace approach to improve the understanding of domestic abuse for employees and managers, identifying appropriate support to those affected, and recognising the impact on children and families. | Recommendation 11 | June 2019 | Clare Platt Head of Health, Equity and Partnerships |
| 1.3.4 | Recommission the Lancashire Domestic Abuse Perpetrator Programme to reduce the risk of reoffending and improve life chances within vulnerable households. | Recommendation 11 | April 2019 | Clare Platt Head of Health, Equity and Partnerships |
| 1.3.5 | Implement the use of Operation Encompass to improve the timeliness of information sharing and support to children experiencing domestic abuse. | Recommendation 11 | February 2019 | Andy Smith Acting Head of Safeguarding, Inspection & Audit (SIA) Jane Booth Chair of LSCB |
| 1.3.6 | Improve the quality and timeliness of police vulnerable person reports to the Multi-Agency Safeguarding Hub (MASH). | Recommendation 11 | March 2019 | Andy Smith Acting Head of SIA |

| Key Area 2: Prevention Lead: Debbie Duffell |
| --- |
| Outcome statement: Effective services are in place to reduce the need for higher level services by ensuring that the right service is delivered, at the right time, by the right people through effective wellbeing and preventative strategies. |
|  | Action | Ofsted Ref | Due | Lead |
| 2.1 | Develop an effective range of early help services |
| 2.1.1 | Develop a multi-agency Early Help Strategy. | Recommendation 1 | September 2019 | Debbie Duffell Head of Children, Family and Wellbeing (CFW) Service |
| 2.1.2 | Work with NHS and social care partners to develop a directory of multi-agency universal and targeted resources across the county. | Recommendation 1 | December 2019 | Clare Platt Head of Health, Equity and Partnerships |
| 2.1.3 | Commission an external edge of care service to reduce the need for children becoming looked after. | Recommendation 1 | September 2019 | Dave Carr Head of Policy, Information and Commissioning |
| 2.2 | Continue to develop effective MASH arrangements |
| 2.2.1 | Improve the timeliness of decision making in the MASH. | Recommendation 1 | Quarterly Monitoring | Andy Smith Acting Head of SIA Ian Whitehead Chair of MASH & Demand Management Board |
| 2.2.2 | Establish early help MASH referral posts to support multi-agency use of the Common Assessment Framework (CAF) tool and identify appropriate early help intervention. | Recommendation 1 | January 2019 | Debbie Duffell Head of CFW Service Andy Smith Head of SIA |
| 2.2.3 | Embed the system of regular case audits in the MASH (including multi-agency audits) to identify themes, inform training and drive activity. | Recommendation 1 and 10 | April 2019 | Andy Smith Acting Head of SIA |
| 2.3 | Embed the use of the Early Help and MASH modules on the Lancashire Child System (LCS) |
| 2.3.1 | Identify and secure multi-agency early help pathways to provide an appropriate level of support and agency response. | Recommendation 1 | April 2019 | Debbie Duffell Head of CFW Service Andy Smith Acting Head of SIA |
| 2.3.2 | Improve and secure appropriate and timely pathways for re-escalation of cases back into Children's Social Care. | Recommendation 1 | April 2019 | Debbie Duffell Head of CFW Service Andy Smith Acting Head of SIA |

| Key Area 3: Purposeful Practice Lead: Bertie Goffe |
| --- |
| Outcome statement: Purposeful and effective social work practice is in place which: engages children, young people and families; builds on their strengths; makes a tangible and positive difference to their lives; and intervenes at the lowest and least intrusive level possible. |
|  | Action | Ofsted Ref | Due | Lead |
| 3.1 | Develop shared values, principles, knowledge and skills |
| 3.1.1 | Ensure that social workers and managers understand the Knowledge and Skills Statement (KSS) and accreditation process and there is a clear plan for how they will be prepared and endorsed for this process. | ALL | March 2019 | Bertie Goffe Principal Social Worker |
| 3.1.2 | Develop a Statement of Social Work in Lancashire, which sets out our values and principles, with clear links to the KSS. | ALL | February 2019 | Bertie Goffe Principal Social Worker |
| 3.1.3 | Develop a clear communications pathway to promote values, aspirations and the shift from compliance to quality. | ALL | March 2019 | Bertie Goffe Principal Social Worker |
| 3.1.4 | Refresh all purposeful practice workshops to ensure that they: Promote the clear values and principles of social work set out in our Statement of Social Work in Lancashire; Promote the KSS; Are centred on the journey of the child; Support the delivery of the Ofsted recommendations. | ALL | March 2019 | Bertie Goffe Principal Social Worker |
| 3.2 | Embed the use of a more strengths based Risk Sensible Model |
| 3.2.1 | Commission bespoke training to support more strengths based practice and taking into consideration the wider workforce. | Recommendation 2, 3, 4, 5, 7, 8, 11 | Plan In place by March 2019 | Victoria Gent Head of Service CSC, East Locality |
| 3.2.2 | Undertake and utilise findings from regular case audits on the use of the strengths based risk sensible approach to inform training and drive practice improvement at a local level. | Recommendation 10 | September 2019 | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC |
| 3.3 | Improve the quality of assessments |
| 3.3.1 | Deliver training based on best practice to ensure the quality of social work assessments is consistently good and is available to all social workers across children's services. | Recommendation 2 | New programme to be delivered from March 2019 | Bertie Goffe Principal Social Worker |
| 3.3.2 | Deliver joint training sessions with Independent Reviewing Officers (IROs) and front-line managers to: Gain a shared understanding of the requirements of a good assessment; Clearly articulate what best practice looks like in accordance with the Ofsted grade descriptors; Enable positive critical challenge and professional respect. | Recommendation 2 | Commence February 2019 | Andy Smith Acting Head of SIA |
| 3.3.3 | Deliver Manager Learning Circles to: Increase knowledge of what a good assessment looks like; Enable confident challenge to front-line staff; Increase the number of signed-off good quality assessments. | Recommendation 2 | Pilot November 2018 Roll out June 2019 | Bertie Goffe Principal Social Worker |
| 3.3.4 | Undertake and utilise findings from regular case audits on the quality of assessments to identify themes, inform training and drive improvement at a local level. | Recommendation 2 and 10 | March 2019 | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC David Graham Acting Head of Inclusion |
| 3.3.5 | Utilise service wide findings from case audits on the quality of assessments to inform activity and secure a consistent county-wide approach. | Recommendation 2 and 10 | March 2019 | Sally Allen Acting Director of CSC David Graham Acting Head of Inclusion |
| 3.4 | Ensure that plans are specific, measureable and outcome-focused |
| 3.4.1 | Deliver training on SMART, child-impact focused plans, available to all staff across CSC, Inclusion Service, and Children with Disabilities Teams. | Recommendation 3 | New programme to be delivered from March 2019 | Bertie Goffe Principal Social Worker |
| 3.4.2 | Deliver joint training sessions with IROs and front-line managers to: Gain a shared understanding of the requirements of a good plan; Clearly articulate what best practice looks like in accordance with the Ofsted grade descriptors; Enable positive critical challenge and professional respect; Ensure understanding of the integration of plans e.g.; Education, Health & Care Plan (EHCP), Personal Education Plan (PEP) and health assessment. | Recommendation 3 | April 2019 | Andy Smith Acting Head of SIA |
| 3.4.3 | Deliver Manager Learning Circles to: Increase knowledge of what a good plan looks like; Enable confident challenge to front-line staff; Increase the number of signed-off good quality plans. | Recommendation 3 | Pilot November 2018 Roll Out June 2019 | Bertie Goffe Principal Social Worker |
| 3.4.4 | Review the current PEP plan template to provide a more effective tool to support educational progress. | Recommendation 3 and 6 | February 2019 | Audrey Swann Virtual School Head Teacher |
| 3.4.5 | Review the current EHCP process to ensure the agreed pathway is fully embedded across all organisations. | Recommendation 3 | January 2019 | David Graham Acting Head of Inclusion |
| 3.4.6 | Undertake and utilise findings from regular case audits on the quality of plans to identify themes, inform training and drive activity at a local level. | Recommendation 3 | September 2019 | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC David Graham Acting Head of Inclusion |
| 3.4.7 | Utilise service wide findings from case audits on the quality of plans to inform activity and secure a consistent countywide approach. | Recommendation 3 and 10 | March 2019 | Sally Allen Acting Director of CSC David Graham Acting Head of Inclusion |
| 3.5 | Improve the quality of critical challenge by first line managers and IROs |
| 3.5.1 | Deliver training on quality and critical challenge through the Leadership Academy, IRO development days and joint training sessions with IROs and front-line managers. | Recommendation 4 | Commence March 2019 | Andy Smith Acting Head SIA |
| 3.5.2 | Deliver Manager Learning Circles with a focus on improving the quality of critical challenge. | Recommendation 4 | Pilot Nov 2018 Roll Out June 2019 | Bertie Goffe Principal Social Worker |
| 3.5.3 | Strengthen reflective supervision with first-line managers to enable reflection on the quality of practice and facilitate quality, critical challenge. | Recommendation 4 | Quarterly Monitoring | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC David Graham Acting Head of Inclusion |
| 3.5.4 | Increase opportunities for peer challenge, shadowing and collaboration with Blackpool and Blackburn with Darwen local authorities. | Recommendation 4 | April 2019 | Sally Allen Acting Director CSC Andy Smith Acting Head of SIA |
| 3.5.5 | Share data, intelligence and themes/ focus with first-line managers to drive activity at a local level and enable appropriate critical challenge. | Recommendation 4 and 10 | February 2019 | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC David Graham Acting Head of inclusion Andy Smith Acting Head of SIA |
| 3.5.6 | Develop guidance for IROs on chairing Children Looked After (CLA) reviews. | Recommendation 4 | January 2019 | Andy Smith Acting Head of SIA |

| Key Area 4: Permanence and Children in our Care Lead: Barbara Bath & Stephen Belbin |
| --- |
| Outcome statements: Children in Lancashire receive the right service at the right time that improves their outcomes. Children are only removed from their family environment where we are able to improve their life chances and outcomes. Where a child does need to come into our care, we ensure that we develop plans for stable and permanent care at the earliest possible opportunity. |
|  | Action | Ofsted Ref | Due | Lead |
| 4.1 | Ensure that children are only brought into care when it is in their best interests to do so |
| 4.1.1 | Share the findings from the Care Crisis Review report and implement a training plan to explore the learning from this. | Recommendation 2, 3, 4, 5, 7, 8, 10, 11 | From January 2019 | Josie Lee Improvement Partner |
| 4.1.2 | Ensure that the Statement of Social Work in Lancashire, clearly sets out the principle that children are only brought into care, when it is in their best interests to do so. | Recommendation 2, 3, 4, 7, | February 2019 | Bertie Goffe Principal Social Worker |
| 4.1.3 | Review the 'Becoming Looked After Panels' and monthly Resource Panels to ensure consistency and effectiveness. | Recommendation 2, 3, 4, 7, 10 | February 2019 | Sally Allen Acting Director of CSC |
| 4.1.4 | Commissioning of a strengths based practice model to embed a culture of working alongside families to develop plans to support children within their families, when safe to do so. | Recommendation 1, 2, 3, 4, 5, 8, 11 | April 2019 | Victoria Gent Head of Service, CSC, East Locality |
| 4.2 | For children looked after using Section 20 of The Children Act 1989, further improve children's written records so it is clear why they are looked after and what the care episode is expected to achieve |
| 4.2.1 | Develop guidance on good practice re Section 20 decision making for social workers and managers. | Recommendation 2, 3, 4, 7, 8 | March 2019 | Andy Smith Acting Head of SIA |
| 4.2.2 | Develop guidance on good practice re the recording of management decisions for social work managers at critical points in the child's journey. | Recommendation 4, 7, 8 | March 2019 | Andy Smith Acting Head of SIA |
| 4.3 | Ensure that effective use is made of local, quality, permanent provision that can meet the needs of Lancashire children |
| 4.3.1 | Deliver training on 'The Right Child, Right Placement.' | Recommendation 3, 4, 7, 8 | From January 2019 | Bertie Goffe Principal Social Worker |
| 4.3.2 | Work collaboratively with agency framework providers to seek to prioritise Lancashire children for Lancashire placements. | Recommendation 2, 3, 9, 10 | Monthly | Dave Carr Head of Policy, Information & Commissioning |
| 4.3.3 | Develop new commissioning arrangements to block purchase up to half of our predictable need for agency children's home placements. | Recommendation 7, 9, 10 | Service to Commence September 2019 | Dave Carr Head of Policy, Information & Commissioning |
| 4.3.4 | Implement and embed Placement Stability Meetings. | Recommendation 7, 8 | Implement January 2019 Review progress April 2019 | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC Barbara Bath Head of FARY David Graham Acting Head of Inclusion |
| 4.3.5 | Undertake analysis of issues impacting on disruptions and use learning to improve procedures and processes. | Recommendation 7, 8, 10 | Quarterly | Andy Smith Acting Head of SIA |
| 4.4 | Embed a consistent and rigorous approach to permanence planning to reduce the likelihood of drift and delay |
| 4.4.1 | Establish a broader definition of permanence and kinship through the Statement of Social Work in Lancashire. | Recommendation 7 | February 2019 | Bertie Goffe Principal Social Worker |
| 4.4.2 | Revise the care planning protocol to ensure processes and policies are clear and understood. | Recommendation 7 | January 2019 | Brendan Lee Head of Service CSC North Locality |
| 4.4.3 | Embed the use of the PLO Permanence Planning Tracker. | Recommendation 7 | Pilot Central January 2019 Roll Out April 2019 | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC David Graham Acting Head of Inclusion |
| 4.4.4 | Deliver training on permanence through care planning. | Recommendation 7 | March 2019 | Bertie Goffe Principal Social Worker |
| 4.4.5 | Ensure that decisions are ratified at the Permanence Panel. | Recommendation 7 | Quarterly Monitoring | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC Barbara Bath Head of FARY David Graham Acting Head of Inclusion |
| 4.4.6 | Embed improved use of Family Group Conferences, particularly at a non-statutory intervention level and at Initial Child Protection Conference. | Recommendation 7 | February 2019 | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC David Graham Acting Head of Inclusion |
| 4.4.7 | Ensure that all CLA living away from parents have a Life Story book/ work completed. | Recommendation 7 | November 2019 | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC |
| 4.4.8 | Monitor Life Storybooks/ work and ensure that this is recorded at CLA reviews. | Recommendation 7 | Quarterly Monitoring | Andy Smith Acting Head of SIA |
| 4.4.9 | Improve the quality of IRO challenge to drift and delay and the quality of plans. | Recommendation 7 | Quarterly Monitoring | Andy Smith Acting Head of SIA |
| 4.4.10 | Ensure permanence has been considered at the second CLA review in all cases. | Recommendation 7 | Quarterly Monitoring | Andy Smith Acting Head of SIA |
| 4.5 | Ensure timely revocation hearings are held to secure permanence plans for children to remain in the care of their parents |
| 4.5.1 | Review all children who are placed at home with parents and seek revocation of orders where appropriate. | Recommendation 8 | March 2019 | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC David Graham Acting Head of Inclusion |
| 4.5.2 | Establish Discharge Panels and tracker to reduce the likelihood of drift and delay. | Recommendation 8 | February 2019 | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC |
| 4.5.3 | Undertake regular audits of new placements made with parents and use learning to further improve practice. | Recommendation 8 | Quarterly Monitoring | Andy Smith Acting Head of SIA |
| 4.5.4 | Improve the quality of written agreements, training and quality assurance. | Recommendation 8 | March 2019 | Andy Smith Acting Head of SIA |
| 4.5.5 | Ensure that management decisions are clearly recorded when children are returning home. | Recommendation 8 | Quarterly Monitoring | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC David Graham Acting Head of Inclusion |
| 4.5.6 | Ensure IRO challenge of drift and delay is evident and effective. | Recommendation 8 | Quarterly Monitoring | Andy Smith Acting Head of SIA |
| 4.5.7 | Audit and share understanding of drivers for high numbers of Home Placement Agreements to inform improved practice. | Recommendation 8 | March 2019 | Bertie Goffe Principal Social Worker |
| 4.6 | Improve the educational attainment and progress of children looked after at Key Stage 4 |
| 4.6.1 | Increase frequency of tracking for Year 9/10/11 pupils who are failing to progress at the expected rate. | Recommendation 6 | Spring Term 2019 | Audrey Swann Virtual School Head Teacher |
| 4.6.2 | Ensure no KS3 or 4 CLA pupil is moved to a location that will require a change of school, (except in urgent circumstances) without a discussion with the Virtual School. | Recommendation 6 | Monthly Monitoring | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC David Graham Acting Head of Inclusion |
| 4.6.3 | Research most effective support in Reading and Maths, including consultation with young people to identify barriers. | Recommendation 6 | April 2019 | Audrey Swann Virtual School Head Teacher |
| 4.6.4 | Use PGG+ high needs funding to support evidence based strategies. | Recommendation 6 | April 2019 | Audrey Swann Virtual School Head Teacher |
| 4.6.5 | Increase Careers, Education, Information, Advice and Guidance (CEIAG) support and opportunities for positive experience of the workplace from Year 10 for our CLA placed in Lancashire schools. | Recommendation 6 | Work Experience -January 2019 CEAIG – Y11 – Sept 2018 Y10 - Sept 2019 | Audrey Swann Virtual School Head Teacher |
| 4.6.6 | Increase training / events for carers (in both residential and foster care) to promote understanding of education systems and their support of progress and attainment. | Recommendation 6 | Spring Term 2019 | Audrey Swann Virtual School Head Teacher |
| 4.6.7 | Increase the percentage of CLA who are educated in mainstream schools. | Recommendation 6 | July 2019 | Audrey Swann Virtual School Head Teacher |
| 4.6.8 | Increase the number of CLA with SEND who have access to the GCSE curriculum. | Recommendation 6 | July 2019 | Audrey Swann Virtual School Head Teacher |
| 4.6.9 | Analyse the outcomes for CYP with SEND and agree targets for improvement. | Recommendation 6 | October 2019 | David Graham Acting Head of Inclusion |
| 4.6.10 | Implement a programme of action with schools to achieve the agreed targets for improvement. | Recommendation 6 | November 2019 | David Graham Acting Head of Inclusion |
| 4.7 | Ensure that care leavers receive timely, accessible support that meets their financial, educational & emotional health needs |
| 4.7.1 | Develop training for all Personal Advisers and other support staff to ensure delivery of the Care Leavers Local Offer through improved planning and implementation of Pathway Plans. | Recommendation 9 and 4 | March 2019 | Victoria Gent Head of Service, CSC East Locality Rachel Rump Skills, Learning and Development |
| 4.7.2 | Provide targeted training to Personal Advisers and other support staff to enable them to better support children and young people with their emotional health needs. | Recommendation 9 | June 2019 | Victoria Gent Head of Service, CSC East Locality Rachel Rump Skills, Learning and Development |
| 4.7.3 | Ensure our commitment to care leavers is clearly articulated in the Statement of Social Work in Lancashire and through training. | Recommendation 9 | February 2019 | Bertie Goffe Principal Social Worker |
| 4.7.4 | Review and amend the Pathway Plan template to provide a more robust and personalised plan with clear targets, strategies and timeframes. | Recommendation 9 and 4 | April 2019 | Rose Howley Acting Head of Service CSC Central Locality |
| 4.7.5 | Embed the use of ASDAN training and accreditation through foster carer and Social Work Academy training. | Recommendation 9 | March 2019 | Rose Howley Acting Head of Service CSC Central Locality |
| 4.7.6 | Provide access for all care leavers who are NEET, to bespoke programmes of support. | Recommendation 9 | March 2019 | Audrey Swann Virtual School Head Teacher Rose Howley Acting Head of Service CSC Central Locality |
| 4.7.7 | Increase opportunities for care leavers to access work experience placements, work shadowing, apprenticeships and employment across Lancashire. | Recommendation 9 | March 2019 | Audrey Swann Virtual School Head Teacher Rose Howley Acting Head of Service CSC Central Locality |
| 4.7.8 | Establish a FE/Virtual School Forum to help develop appropriate courses and increase support for care leavers. | Recommendation 9 | March 2019 | Audrey Swann Virtual School Head Teacher |
| 4.7.9 | Provide opportunities for care leavers to increase their knowledge, understanding and experience of higher education. | Recommendation 9 | April 2019 | Audrey Swann Virtual School Head Teacher Rose Howley Acting Head of Service CSC Central Locality |
| 4.7.10 | Ensure that CLA and care leavers with SEND have their healthcare needs identified, assessed and met, and that there is oversight across the local area. | Recommendation 9 | February 2019 | Sally Allen Acting Director of CSC |

| Key Area 5: Effective Use of Performance Data Lead: Brendan Lee |
| --- |
| Outcome statements: We know ourselves well, understand where our services are doing well and where we need to improve. Using the information we gain from service data and performance review processes to make decisions which make a difference to the lives of children and families. |
|  | Action | Ofsted Ref | Due | Lead |
| 5.1 | Improve the use of performance data so that it is an effective tool to help managers measure progress and examine trends |
| 5.1.1 | Develop a robust performance framework which gathers performance and intelligence from across Children's Services. | Recommendation 10 | February 2019 | Brendan Lee Chair of Data, Quality and Performance (DQP) Group - Head of CSC North Locality |
| 5.1.2 | Review existing mechanisms and reports to ensure that they support effective, efficient and timely analysis and recommendations. | Recommendation 10 | February 2019 | Brendan Lee Chair of DQP Group - Head of CSC North Locality |
| 5.1.3 | Incorporate data and analysis from partners into the performance framework. | Recommendation 10 | March 2019 | Brendan Lee Chair of DQP Group - Head of CSC North Locality |
| 5.1.4 | Through the effective use of data Identify the most effective early help interventions and demonstrate the impact of those interventions on diverting demand from statutory services. | Recommendation 10 and 1 | April 2019 | Debbie Duffell Head of CFW Service |
| 5.1.5 | Complete and publish a Joint Strategic Needs Analysis (JSNA) to support understanding of health, social care and education need across the local area. | Recommendation 10 | March 2019 | Sally Richardson Principal Educational Psychologist |
| 5.1.6 | Develop a shared data dashboard communicating shared performance measures to inform CYP, parent/carers and stakeholders of progress. | Recommendation 10 | April 2019 | David Graham Acting Head of Inclusion |
| 5.1.7 | Utilise data and intelligence provided through the performance framework to identify themes and inform training. | Recommendation 10 | December 2018 | Brendan Lee Head of Service CSC North Locality |
| 5.2 | Further develop audit reporting to be more analytical and more effectively used by managers |
| 5.2.1 | Deliver a programme of monthly and themed audits and reporting of key findings and associated actions. Revision of QA framework to include a more holistic overview of practice. | Recommendation 10 | Monthly Reports | Bertie Goffe Principal Social Worker |
| 5.2.2 | Increase the quality and quantity of analysis in audit reports. | Recommendation 10 | March 2019 | Bertie Goffe Principal Social Worker |
| 5.2.3 | Deliver audit training and one-to-one support to managers to support completion of higher quality audits and utilisation of findings to improve practice. | Recommendation 10 | May 2019 | Bertie Goffe Principal Social Worker |
| 5.2.4 | As part of the Quality Assurance Framework introduce Practice Weeks. | Recommendation 4 | April 2019 | Andy Smith Acting Head of SIA |
| 5.2.5 | Implement the EHCP quality standards and audit framework. | Recommendation 10 and 4 | January 2019 | David Graham Acting Head of Inclusion |
| 5.2.6 | Train and support all SEND auditors to ensure consistency of approach. | Recommendation 10 | February 2019 | David Graham Acting Head of Inclusion |
| 5.2.7 | Audit all EHCPs at transition to secondary school. | Recommendation 10 and 4 | June 2019 | David Graham Acting Head of Inclusion |
| 5.2.8 | Audit all new EHCPs issued from January 2019 within the first year. | Recommendation 10 and 4 | December 2019 | David Graham Acting Head of Inclusion |
| 5.2.9 | Further embed learning from customer feedback and evidence how this has been used to improve practice. | Recommendation ALL | May 2019 | Andy Smith Acting Head of SIA |

| Key Area 6 Workforce Development Lead: Victoria Gent |
| --- |
| Outcome statements: Maintain the recruitment of dedicated staff and ensure vacant posts are permanently recruited to. Improve the retention of skilled, experienced staff within the children's workforce. Development of a knowledgeable, skilled and resilient children's workforce able to deliver improved outcomes for children. A consistent approach to health and wellbeing of our workforce as a key enabler of long term professional success and central to our staff retention. |
|  | Action | Ofsted Ref | Due | Lead |
| 6.1 | Maintain the recruitment of staff |
| 6.1.1 | Continue rolling recruitment programme and centralised panels for Children's Social Care. | ALL | Review Quarterly | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC |
| 6.1.2 | Continue to develop the Social Work Academy for all new social workers to Lancashire as part of our workforce strategy. | Recommendation 2, 3 | Review June 2019 | Bertie Goffe Principal Social Worker |
| 6.1.3 | Support current employees to become social work qualified through a "Grow your Own scheme." | ALL | April 2019 | Rachel Rump Skills, Learning & Development |
| 6.1.4 | Development of the Teaching Partnership to maximise the number of placements available to students by increasing the number of statutory placements from 1 to 2 per student across the partnership (LCC, Blackpool and Blackburn with Darwen) by the end of academic year 2019/20. | ALL | March 2020 | Rachel Rump Skills, Learning & Development |
| 6.1.5 | Reduction of agency staff to less than 5 %. | ALL | Review Monthly | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC |
| 6.2 | Reduce staff turnover in children's services |
| 6.2.1 | Revise the quarterly children's services workforce profile to provide detailed understanding of retention across the county, including internal movement and the reasons for the use of agency staff. | ALL | March 2019 | Victoria Gent Head of Service CSC East Locality |
| 6.2.2 | Improve the use of the Grade 9 (senior practitioner) panel process. | ALL | April 2019 | Victoria Gent Head of Service CSC East Locality |
| 6.2.3 | Establish an updated career pathway with routes for aspiring managers and those who want to remain in practice. | ALL | July 2019 | Victoria Gent Head of Service CSC East Locality |
| 6.2.4 | Updated staff "health check" to be completed to ascertain the views of staff. | ALL | May 2019 | Bertie Goffe Principal Social Worker |
| 6.2.5 | Evaluation of Leadership Academy to be completed. | ALL | April 2019 | Rachel Rump Skills, Learning & Development |
| 6.2.6 | Promote the recognition of staff in an annual children's services awards event. | ALL | September 2019 | Debbie Cookson Team Manager Advanced Practitioners |
| 6.2.7 | Ensure all managers are briefed on the key building blocks of good staff retention. | ALL | April 2019 | Victoria Gent Head of Service CSC East Locality |
| 6.2.8 | Ensure staff have manageable, appropriate caseloads. | ALL | Review Monthly | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC David Graham Acting Head of Inclusion |
| 6.2.9 | Review the current performance scorecard in relation to the workforce, including staff experience and Assessed & Supported Year in Employment (ASYE) numbers. | ALL | March 2019 | Victoria Gent Head of Service CSC East Locality |
| 6.3 | Improve the development of the workforce |
| 6.3.1 | Revise and refresh the current training offer, ensuring it is aligned with the Ofsted inspection recommendations and key priorities, including strengths based practice, neglect and domestic abuse. | ALL | March 2019 | Victoria Gent Head of Service CSC East Locality Bertie Goffe Principal Social Worker Rachel Rump Skills, Learning & Development |
| 6.3.2 | Support and prepare staff for the National Accreditation Scheme. | ALL | Workshops to commence September 2019 | Victoria Gent Head of Service, CSC East Locality Bertie Goffe Principal Social Worker Rachel Rump Skills, Learning & Development |
| 6.3.3 | Continue to embed the KSS in all management frameworks. | ALL | March 2019 | Brendan Lee Victoria Gent Rose Howley Locality Heads of CSC |
| 6.3.4 | Promote opportunities for experienced staff to become practice educators, increasing the quantity and quality of practice learning placements. | ALL | Review Quarterly | Rachel Rump Skills, Learning & Development |
| 6.3.5 | Continue to provide a robust and well supported first year in practice that focuses on development and resilience. | ALL | Review June 2019 (As part of SW Academy Review) | Bertie Goffe Principal Social Worker Rachel Rump Skills, Learning & Development |
| 6.3.6 | Analysis of exit interviews to inform understanding of those leaving Lancashire. | ALL | Quarterly Report | Debbie Cookson Team Manager Advanced Practitioners |
| 6.4 | Support the health and wellbeing of our staff |
| 6.4.1 | Ensure flexible working policies are applied consistently across the county to promote work life balance. | ALL | Review Quarterly | Victoria Gent Head of Service CSC East Locality All Heads of Service |
| 6.4.2 | Development of health and wellbeing champions across children's services to improve localised initiatives. Development of quarterly Champions Board meeting. | ALL | April 2019 | Victoria Gent Head of Service CSC East Locality |
| 6.4.3 | Promote the health and wellbeing of staff as part of supportive, reflective supervision. | ALL | Quarterly Monitoring | Bertie Goffe Principal Social Worker Victoria Gent Head of Service CSC East Locality |
| 6.5 | Monitor our performance on the 4 key work streams of the workforce strategy |
| 6.5.1 | Review and refresh the current workforce performance scorecard | ALL | March 2019 | Victoria Gent Head of Service CSC East Locality |

How we will know we are making a difference

| What Our Children Will Say: | What Our Partners Will Say: |
| --- | --- |
| Effective Partnership Working | Effective Partnership Working |
| Prevention | Prevention |
| Purposeful Practice | Purposeful Practice |
| Permanence and Corporate Parenting | Permanence and Corporate Parenting |
| Effective Use of Performance Data | Effective Use of Performance Data |

Appendix 1: Governance Structure

Appendix 2: Library of Plans: delivering improvement and change

# Text boxes

Lancashire Getting to Good Plan

January 2019

Date to be reviewed: April 2019

Associated performance trackers to be reviewed every six weeks.

Plan to be reviewed and updated as required.

Plan to be reviewed and updated as required.

I have one key worker who I trust and who knows me well.

I don't keep having to tell my story to lots of different people.

We are working together towards a clear vision and shared culture for improving children's services.

I know who to talk to if I feel worried or frightened.

I am happy and feel safe.

We understand and respect each other's contribution and role.

We work together within a shared framework.

I understand why I have a social worker and how they will help me and my family. My life feels better.

I trust my social worker and I know them well.

We work together effectively.

Our meetings are purposeful and inclusive.

We share risks effectively. We feel equal partners.

My social worker understands the important things that have happened to me in the past and talks to all the people who have important information to help me.

I receive the information to help me to be successful in adult life, at the time I need it.

The council is getting better at being a corporate parent.

We are clear about our role and contributions as corporate parents.

Managers who run the service use accurate information about how services are doing, so they can improve the right things.

We share and utilise data and intelligence effectively to ensure that we are delivering good services.

Lancashire Safeguarding Children Board

- Oversight and scrutiny of delivery to children in need and in need of protection

- Neglect strategy

- Domestic abuse strategy

- Planning of services

- Reviews of serious cases

Corporate Management Team

- Oversight and support for improvement and change

Cabinet

- Oversight of leadership management and governance of Children's Social Care, Education and Partnerships

Finance and Monitoring Board: Chair - Head of Service Financial Management (Operational)

Monthly Safeguarding Reviews

- Leader and CEO Oversight of leadership, management and governance of Children's Social Care

Corporate Parenting Board

- Oversight and scrutiny of permanence and corporate parenting delivery

Getting to Good Board

- Communication strategy

- Monitor whole system improvement and plan delivery

Children's Partnership

Multi-agency early help

Data Quality and Performance Board

Self-assessment - Data delivery improvement and use of data

Purposeful Practice Board

Delivers change in social work practice – quality and compliance

MASH and Demand Management Board

Delivers coordinated demand management strategy and quality front door

Permanence and Children in our Care Board

Workforce Development Board

Recruitment - Health and wellbeing – Retention - Skills and knowledge

Deliver improvement through projects and change activities

Under development

Transitioning to BAU