**Hillhouse Technology Enterprise Zone – Lead Rob Green**

**Background**

In April 2016 the Government awarded Enterprise Zone status to Hillhouse Technology Enterprise Zone.Hillhouse EZ has benefited from private sector investment including a gas fired generator station Burn Naze IE, c.30,000 sq ft extension at Addisons Projects, Victrex’s c.20,000 sq ft R&D plant and completion of AGC CE’s thermal oxidiser. Victrex received circa £1.4m Regional Growth Fund toward the R&D pilot plant which is the only significant public sector investment to date.

**Performance**

|  |  |  |  |
| --- | --- | --- | --- |
| **KPI Description**  | **Target to 2026** | **Actuals (Q3 20/21)** | **RAG** |
| Commercial / R&D floorspace (sqm) | 13,000 | c.4,600 |  |
| Jobs Created | 137 | 58 |  |
| Land Sales  | £1.5m | - |  |

Amber RAG has been applied to reflect two key matters:

* The history and layout of the site suits large investments, which take a considerable amount of time to develop, as such the impact of Covid is more likely to have a stronger impact here. However when they do take place, they will have a considerable positive impact upon KPIs.
* Performance is strongly linked to the delivery of the Getting Building Fund project which brings forward (quicker than relying solely on EZ funds) smaller land parcels to a more open market, however there is currently some uncertainty about the timely delivery of this project, and so this impacts upon the confidence of output delivery.

|  |  |
| --- | --- |
| **Baselines at April 2016** |  |
| Jobs Created | 1650 |
| Companies on site  | 45 |
| Business rates  | £2.5m |

|  |  |
| --- | --- |
| **Milestones** | **Dates** |
| LFFN (Local Full Fibre Network roll out) to site boundary | Complete |
| Revised Delivery Plan  | Nov 2020 |
| Demolition and site clearance of Vinnolit site to commence  | Dec 2020 |
| 60,000 sq ft speculative development of small multi-use units planning submitted  | Q4 2020 |
| Appointment of joint international marketing agent LAMEC brand  | Jan 2021 |
| Fiscal benefit extension decision from HM Treasury | Mar 2021 |
| Forsa Energy completion of build  | Spring 2021 |
| Demolition and clearance of Vinnolit plots complete  | Summer 2021 |
| Subsequent roll out of fibre ducting on site  | Dec 2021 |
| Utilities and infrastructure upgrade including new gatehouse | Jan 2022 |

**Objectives over 2 years:**

LFFN roll out across site complete

Commencement of spec dev build of 60,000 sq ft multi-use units

Utilities and infrastructure work including new gatehouse complete

Railway Line

**Objectives over 5 years:**

Phase 1 spec build complete and fully let

Phase 2 new spec development in planning pipeline

Access Road

**Objectives over 10 years:**

50% of site built out and thriving business hub

**Risks**

A new Single Portfolio Risk Register for the combined programmes has been created, which can be found at Appendix M to the main report.