**FOREST OF BOWLAND AONB JOINT ADVISORY COMMITTEE**

**Revised AONB Management Plan Review Timetable (08/04/2013)**

|  |  |  |
| --- | --- | --- |
| **Review Stage** | **Timetable** | **Comment** |
| Agree outline Review methodology | Complete | AONB Funders Group  |
| Launch of Management Plan Review | Complete | Extraordinary AONB JAC meeting |
| Agree extent of the Review | Complete | Preliminary consultation with AONB JAC at meeting |
| Write to the local authorities to agree terms of reference for the preparation of the Review | Complete | AONB Unit |
| Issue statutory notice regarding the Review | Complete | MP Review Working Group |
| Outline Plan structure agreed | April 2013 | MP Review Working Group |
| Public consultation events  | May/June 2013 | AONB Unit and Consultants? |
| Draft Plan produced  | Early July 2013 | MP Review Working Group |
| Public on-line consultation on Draft Plan | July 2013 | AONB Unit |
| Technical consultation events | July 2013 | AONB Partnership |
| Full Draft Plan produced | August 2013 | MP Review Working Group |
| Strategic Environment Assessment (SEA) | September 2013 | AONB Unit and LCC |
| Sustainability Appraisal (SA) | September 2013 | AONB Unit |
| Equality Impact Assessment (EqIA) | September 2013 | AONB Unit and LCC |
| Natura 2000 sites Appropriate Assessment (AA) | September 2013 | AONB Unit and LCC |
| Public on-line consultation on Full Draft Plan and SEA/AA/SA/EqiA | September – October 2013 | AONB Unit |
| Final Management Plan produced | December 2013 | Final version of the PlanMP Review Working Group |
| Final Management Plan to Local Authorities for adoption | January 2014 | Plan adopted by LAs after confirmation by Defra/NE that plan satisfies statutory requirements |
| Presentation to Minister/Defra of approved plan | March 2014 | Plan forwarded to Defra |