**AGENDA ITEM 10b**

Forest of Bowland AONB Management Plan - Revised Review Timetable (09/10/2013)

|  |  |  |
| --- | --- | --- |
| **Review Stage** | **Timetable** | **Comment** |
| Agree outline Review methodology | Complete | AONB Funders Group |
| Launch of Management Plan Review | Complete | Extraordinary AONB JAC meeting |
| Agree extent of the Review | Complete | Preliminary consultation with AONB JAC at meeting |
| Write to the local authorities to agree terms of reference for the preparation of the Review | Complete | AONB Unit |
| Issue statutory notice regarding the Review | Complete | MP Review Working Group |
| Outline Plan structure agreed | Complete | MP Review Working Group |
| Public consultation events | Complete | AONB Unit and S Robinson Consulting |
| Draft Plan produced | Complete | MP Review Working Group |
| Technical consultation events | Complete | AONB Unit Partnership |
| Full Draft Plan produced | End October 2013 | AONB Unit & MP Review Working Group |
| Strategic Environment Assessment (SEA) | October 2013 | AONB Unit and LCC |
| Initial SEA Review of the Plan | October 2013 | AONB Unit |
| Public on-line consultation on Full Draft Plan and SEA/AA/SA | Commences late October 2013 | AONB Unit |
| Equality Impact Assessment (EqIA) | November 2013 | AONB Unit and LCC |
| Natura 2000 sites Appropriate Assessment (AA) | November 2013 | AONB Unit and LCC |
| Revision of the Full Draft Plan | November – December 2013 | AONB Unit |
| Final Management Plan produced | January 2014 | Final version of the Plan  MP Review Working Group |
| Environmental Report consultation | January 2014 | AONB Unit |
| Final Management Plan to Local Authorities for adoption | January - March 2014 | Plan adopted by LAs after confirmation by Defra/NE that plan satisfies statutory requirements |
| Presentation to Minister/Defra of approved plan | March 2014 | Plan forwarded to Defra |