| N'hood Area | Priority | Outline | Possible Actions? | Lead Officer | Action to Date |
| --- | --- | --- | --- | --- | --- |
| Chorley Town East Group Chair – Cllr M Lowe | Alleys and Back Streets | Improve the cleanliness & environment through a combination of interventions including resurfacing; weed spraying, patrol and clean up and use of alley gates. | Prioritised list of alleys and back streets.Seek residents views on possible actions. Extent weed spray contract to include identified alleys | Paul Lowe - HEN | 3 Year Programme agreed: Year 1- Rear of Mayfield Road, Briercliffe Road. Rear of Eaves Lane, alley between Kershaw St and Stump Lane. Rear of Stratford Road, alley entrance from rear of Stump Lane and rear of Primrose Street. Rear of Bannerman Terrace and Garfield Terrace. Consultation stage with residents now being executed |
| Chorley Town East Group Chair – Cllr M Lowe | Improving health literacy and access to health/ wellbeing activities | Creating a health hub in the neighbourhood area using existing community assets. Using voluntary and expanding existing health provision to provide health and wellbeing services locally. Using a canal improvement activity to mobilise the community into exercise. | Engage PCT/CCG and CRT. Identify community assets – Tatton etc. Identify and support existing groups to extend their offer Create a programme of health related services using existing and new provision. Launch using a canal clean up as a starting community activity. | Paul Carter- HEN | We have met with LCC Public Health Professionals to further understand the concept of Health Literacy and the existing toolkits available. CBC supported Health Mela on Saturday 29th June at Tatton Community Centre. We have met with representatives at Tatton Community Centre to discuss the proposal to utilise it as a local health hub. The Health Calendar activities so far have focused on Chorley Town East wherever necessary. Q&A session with CCG and community arranged for late November at Tatton |
| Chorley Town East Group Chair – Cllr M Lowe | South Ave – Environmental Improvements | Area of land requiring improvement through the provision of managed open space including the possible provision of allotments | Consult residents on a range of possible improvements Draw up a scheme that meets the results of the consultation. Plan the delivery of the scheme Undertake works | Jo Oliver- SLC | Land ownership enquiries have been made and this area of land is owned by the housing developer, Barratts. This parcel of land is not part of the S106 agreement for the nearby housing estate. An approach will need to be made to Barratts to see if they would be willing to allow the Council to improve the land before any consultation with residents can start. |
| Chorley Town West Group Chair – Cllr P Phipps | Utilisation of existing recreation and open space with particular reference to Coronation Recreation Ground and Buttermere Green | Increase and encourage greater community use of space. Provide a programme of event and activity. Improve maintenance | Change in maintenance regime. Improvements for tennis courts -safety issues to be addressed. Consultation with residents about potential utilisation schemes | Bob Webster - SLC | Meeting with Cllr Phipps at Coronation and repair work to paths identified. Cllr Snape informed. Identified that £50k allocated to Coronation Rec 2014/15 to resurface and improve tennis courts as long term plan. Drainage survey identified some drainage issues and the work will need to go out to tender and increase in estimated costs. Community Development and Sports teams to support groups to increase use. Work on pathways at Buttermere Green being undertaken as part of wider project linked to development of Community Centre. Repair work to paths at Coronation Rec programmed |
| Chorley Town West Group Chair – Cllr P Phipps | Action to improve hedge and trees on private land that give rise to light interference issues and anxiety in relation to safety. | Several areas of private land have overgrown trees/planting impacting on neighbouring land and property. Establish a FOC or subsidised tree service with info to landowners on impact of overgrown vegetation | Determine extent of issue. Review tree policy. Develop information programme. Consult LCC, RSL’s and residents. Design service | Bob Webster - SLC | Completed. Business as usual within new tree policy, which has been accepted by members. |
| Chorley Town West Group Chair – Cllr P Phipps | Improvements to Hallwood Allotments agreed at June 13 meeting as an alternative to original proposal. | Improvement to 3 plots so that they can be re-let | Plot number 262 – Complete clearance and get in good condition ready to let as 2 separate allotments Plot number 234 & 232 – Fell & remove 3 mature conifers, reduce other 4 | Sarah Leach - SLC | Streetscene to carry out proposed works to 3 plots once agreed with local Cllrs/representatives. Works being completed by Streetscene. |
| Eastern Parishes Group Chair – Cllr M Gray | Business Map Website for Eastern Parish Villages | Develop a website that provides details and promotes local business in the Eastern Parishes | Consult with local business. Website design. Identify local community group or volunteer effort to engage. Establish control/editorship of site | Nuala Lewis – ECDEV | Initial business data cleansing exercise underway and will filter out Eastern Parishes data to produce a mapped subgroup business location plan for our website. |
| Eastern Parishes Group Chair – Cllr M Gray | Provision of open space amenity on currently waste packet of land at Boars Head Hoghton | Create an area of seating and sympathetic planting on an area of waste ground to improve both visual amenity and create a useful open space for residents of the village | Consult with Cllr Dickinson on potential ideas and options. Draw up plans based on information gathered Consult wider community and cost up proposals. Implement works | Lesley Miller- HEN | Plans submitted to Cllr Dickinson for him to consult on options with land owner and PC. Options being priced. |
| Eastern Parishes Group Chair – Cllr M Gray | Repair cobble/set walkway at Victoria Street Wheelton |  |  | Doug Cridland – SLC | Site meeting with Cllr Hansford to discuss scope of project. Agreed to examine possibility of improving surface of cobbled walkway for pushchairs (users of nursery), inc gate and steps; |
| Western Parishes Group Chair – Cllr D Dickinson | Increasing community resilience to flood risk and improving community flood response in the event of a flood. | Croston is a flood risk area and is subject to proposals to improve flood defence both from surface water and river flooding through projects being undertaken by UU and the EA. There is an additional need to support the community resilience to flood events and response during a flood as well as in the recovery stage. | Bid into Community Pathfinder fund. Support establishment of FAG. Public meetings/ engagement. Support survey/mapping work. Improve sandbag provision | Simon Clark- HEN | Lower Yarrow Flood Action Group (LYFAG) established and in direct liaison with Croston Parish Council. Parish Council have agreed oversight of LYFAG spend as part of neighbourhood priorities. Env Agency in partnership with UU and CBC have held an initial consultation on flood defence options. LYFAG supported by CBC conducted a successful a ditch clearing day on 15th June. |
| Western Parishes Group Chair – Cllr D Dickinson | Resolve the use of Back Lane/Sarah Lane/ Bamford Lane Bretherton as a ‘Rat Run’ past the village | This minor road is used repeatedly as a cut through Bretherton despite ‘access only’ signs. Action required to deter its use | Enforcement of existing traffic Order. Awareness raising of the status of the road. Deterrent measures installed | Paul Lowe - HEN | Site visited to identify the problem area and any residences or businesses that are accessible on the route. The 2 routes have also been timed and checked to determine if the cut through is the quicker option- it was not the faster choice. Key stakeholders are now being identified to include the elected members for the area for a meeting to be convened to discuss the project in more detail. |
| Western Parishes Group Chair – Cllr D Dickinson | Social Isolation - Increase participation in activities to reduce isolation particularly amongst the elderly population and young families. | Improve the range of village events and the ability to network between community groups across villages. Networking existing groups and activities; increasing volunteering capacity and publicising offers would address this | Establish the current offer and range of community groups. Transport links between villages at times of activities | Simon Clark- HEN | Survey of over 50’s demographic undertaken. Identified majority of respondents engaged with local groups but a barrier to engagement is transport to events and the timing of events. Work starting on projects to address these issues. |
| Southern Parishes Group Chair – Cllr H Heaton | Play and Open Space provision in the area with particular reference to establishing a play area in Charnock Richard area and additional provision in Coppull | Proposal to create a parking area for the church and community centre and a woodland retreat area at Orchard Garden Charnock Richard. Additional provision of play equipment already recognised for Coppull- Longfield | Increase/encourage volunteer effort. Facilitate networking of groups. Review and extend activity offer | Bob Webster - SLC | Options presented to PC and design agreed. CBC to assist in preparatory works including tree survey, eco survey and planning app. PC to find funds for implementation of works. Play provision in Coppull being considered as part of the Play and Open Space strategy. Waiting for procurement for tree survey to be agreed. |
| Southern Parishes Chair – Cllr H Heaton | Redevelopment of land with garages at Byron Crescent. | Area of land with dilapidated garages being a source of ASB. Seek demolition of garages and establish future us of the land | Confirm land ownership and use of garages. Seek demolition of buildings and clear land. Consult on possible future uses of land. | Lesley Miller- HEN | Works completed to demolish garages. Cllrs asked to consider future development options for next round of Neighbourhood Working projects |
| Southern Parishes Chair – Cllr H Heaton | Review and improve accessibility to the Southern parishes villages in relation to parking provision and accessibility of shops and amenities | Extend economic development activity to outlying villages with more targeted promotion of village centres. | Establish needs and consult on actions required to support villages. Provide small grants to enhance shop fronts Review accessibility and parking provision | Gill Barton – ECDEV | The Council is adding a Southern Parishes Shop Floor Refurbishment Grant/Business Rate Subsidy scheme to the portfolio of available Chorley grants, in the Local Service Centres of Charnock Richard, Heskin and Coppull. The project paperwork is in place and placed on the Chorley website, and additional marketing will be carried out. |
| South East Group Chair – Cllr J Molyneaux | Road Safety – Speed control and road safety awareness | Procure and deploy SPIDs on a programmed rota of sites using trained CBC, community and PC people. Develop a local speed awareness campaign utilising existing road safety resources | Purchase SPID machines. Develop programme for deployment, and train staff to fix at existing fitted locations. Start campaign to raise speed awareness in identified areas. | Paul Lowe - HEN | Multi-agency/ members meeting, four areas have been identified as requiring the devices, Rivington, Adlington, Anderton and Heath Charnock. The next stages for the project will be to purchase the SPiDs and arrange deployment and to develop and implement, along with the communications team, the road safety awareness campaign linked to this project. Training organised for September. |
| South East Group Chair – Cllr J Molyneaux | Estate Parking | Joint work with LCC and CCH to tackle increasing parking issues on some estates in the area. | Identify priority estates/streets for action. Agree consistent policy for drop kerb and verge crossings. Awareness campaign for considerate parking | Jo Oliver- SLC | Members of the SE Parishes group have been contacted and asked for details of problem areas. These will be collated with a draft action plan circulated to the group by the end of July. |
| South East Group Chair – Cllr J Molyneaux | Community Food Growing | Chester Place identified as food growing area. Work with CCH and LWT to start a community food growing group | Provision of raised beds. Provision of equipment/plants Mobilise community group and volunteer effort | Lesley Miller- HEN | Natalie has met with CCH. Initial consultation event carried out at Fairview Youth & Community Centre. Sam Horsby officer from CCH leading on this. 10-15 interested people. Mike Murphy needs to address some land issues regarding on-going maintenance. |
| Clayton & Whittle-le-woods Group Chair – Cllr E Bell | Footpath network around Martins Farm WLW – path no.s 15, 16, 17 and 18. Area of path missing and requires making up. | Complete the footpath network in WLW area where the path is missing | Establish the extent of new path required and works involved.. Explore range of local community groups who would support work Cost the works required. Either contract works , utilise supervised volunteering effort or a combination | Simon Forster - SLC | Work scoped, quotations obtained and work completed. Arranging a date for ‘opening’ |
| Clayton & Whittle-le-woods Group Chair – Cllr E Bell | Provision of a Youth Shelter in WLW area | Provide a youth shelter at an agreed location | Consult residents, youth groups and young people on preferred location; style and design of youth shelter. Draft a scheme. Seek external funded support | Lee Boyer- HEN | Scoping of this project to start quarter 3 |
| Clayton & Whittle-le-woods Group Chair – Cllr E Bell | Tree maintenance programme in Clayton Brook | Utilise existing tree management capability to introduce a programme of tree maintenance and removal in Clayton Brook area | Establish partner tree maintenance programmes Seek to combine and coordinate programmes. Consult residents on additional tree work required. Implement programme | Bob Webster - SLC | Info regarding Tree policy and LCC enforcement gone to group for approval, awaiting final response. Tree team carrying out work as part of long term schedule. |
| Euxton, Astley & Buckshaw Group Chair – Cllr A Platt | Enhancing the eastern approach to Euxton village with environmental screening. | Proposal to undertake some planting/ screening on the approach to Euxton from Ackhurst. Use of trees, planting and other environmental screening | Meeting arranged with Cllr Goldsworthy to scope. Explore orchard planting. Boundary ‘welcome’ stone | Bob Webster - SLC | Land owners identified as Runshaw College on Euxton Lane. Tarmac Co. have carried out some work to quarry entrance on Dawbers Lane. CBC to carry out sympathetic planting to our land around junction with central Ave and other land owners to be approached. Planning to be approached regarding Euxton design guide to ensure future development is appropriately landscaped and existing screening is retained or replaced with similar- enquiries ongoing. |
| Euxton, Astley & Buckshaw Group Chair – Cllr A Platt | Improving the roadside planting to Chancery Road Astley including work to the green space at the school entrance. | Improve ‘blind spot’ on exit from school to Chancery Road. Assess current planting in area and replace some tree planting with low level plants | Scope applicable work Engage school, LCC, PC Scheme design implementation | Bob Webster - SLC | Plan developed to be circulated to group and site meeting to be organised. |
| Euxton, Astley & Buckshaw Group Chair – Cllr A Platt | Review the parking, planting and footpath provision at Greenside Euxton with a view to developing a multi-agency scheme of improvements. | Assessment of area with respect to parking, pedestrian and open space provision. | Consult with CCH, LCC and residents on possible solutions | Lesley Miller- HEN | Plan developed to be circulated to group and site meeting to be organised. Work done by Streetscene as Business as usual, Cllrs to be asked if they want to invest in additional works, estimated additional cost of 2K- so this will remain allocated to project for time being. |