**Appendix 'B'**

**FOREST OF BOWLAND AONB JOINT ADVISORY COMMITTEE**

**AONB Management Plan - Revised Review Timetable**

|  |  |  |
| --- | --- | --- |
| **Review Stage** | **Timetable** | **Comment** |
| Agree outline Review methodology | Complete | AONB Funders Group |
| Launch of Management Plan Review | Complete | Extraordinary AONB JAC meeting |
| Agree extent of the Review | Complete | Preliminary consultation with AONB JAC at meeting |
| Write to the local authorities to agree terms of reference for the preparation of the Review | Complete | AONB Unit |
| Issue statutory notice regarding the Review | Complete | MP Review Working Group |
| Outline Plan structure agreed | Complete | MP Review Working Group |
| Public consultation events | Complete | AONB Unit and S Robinson Consulting |
| Draft Plan produced | Complete | MP Review Working Group |
| Technical consultation events | Complete | AONB Unit |
| Full Draft Plan produced | Complete | AONB Unit & MP Review Working Group |
| Public on-line consultation on Full Draft Plan | Complete | AONB Unit |
| Initial Strategic Environmental Assessment Review of the Plan | Complete | AONB Unit |
| Equality Impact Assessment (EqIA) | February 2014 | AONB Unit and LCC |
| Natura 2000 sites Appropriate Assessment (AA) | February 2014 | AONB Unit |
| Environmental Report consultation | February 2014 | AONB Unit |
| Revision of the Full Draft Plan | Complete | AONB Unit |
| Final Draft Management Plan produced | Complete | Final version of the Plan  MP Review Working Group |
| AONB JAC meeting | 10th February 2014 | Extraordinary JAC to coincide with 50th Anniversary. |
| Final Draft Management Plan to Local Authorities for adoption | February - March 2014 | Plan adopted by LAs after confirmation by Defra/NE that plan satisfies statutory requirements |
| Design of Management Plan finalised | February – March 2014 | AONB Unit, Countryscape |
| Presentation to Minister/Defra of approved plan | April 2014 | Plan forwarded to Defra |