# AONB Unit Business Plan 2014-2017

## Introduction

The Forest of Bowland Area of Outstanding Natural Beauty (AONB) is one of England’s finest landscapes and is internationally important for its heather moorland, blanket bog and rare birds. The special qualities of the area which contribute to its distinctive 'sense of place' can be summarised as:

Wild open spaces

A special place for wildlife

A landscape rich in heritage

A living landscape

Delicious local food and drink

A place to enjoy and keep special

The AONB designation means that the natural beauty of the landscape should not only be conserved and enhanced, but also that recreation and sustainable development should be promoted to help to sustain the landscape and its communities.

## The AONB Partnership and Unit

The AONB is managed by a partnership of local councils, utility company, landowners, farmers, voluntary organisations, wildlife groups, recreation groups, and government agencies, who work to protect, conserve and enhance the natural and cultural heritage of this special area.

The Partnership is funded by eight local authorities (Craven District Council, Lancashire County Council, Lancaster City Council, North Yorkshire County Council, Pendle Borough Council, Preston City Council, Ribble Valley Borough Council, Wyre Council), United Utilities and the Department for Environment Farming and Rural Affairs (Defra).

The AONB Unit is the staff team, who are employed on behalf of the AONB Partnership, to prepare and implement the statutory AONB Management Plan.  The team comprises six people (4.4 full-time equivalents), with additional support from the 'Networks of Nectar' Project Officer (funded up to September 2015), two LCC Senior Environmental Project Officers and LCC Ranger Service.

## A Plan for the Future

This business plan sets out how the AONB Unit will contribute to the work of the Partnership in achieving the long-term vision for the AONB:

"The Forest of Bowland AONB retains its sense of local distinctiveness, notably the large-scale open moorland character of the Bowland Fells, traditional buildings and settlement patterns of villages, hamlets and farmsteads. Natural and cultural heritage is sympathetically managed and contributes to a sustainable and vibrant local economy. The management of the AONB has improved the quality of the landscape for all."

The AONB Unit is working towards four key outcomes:

An outstanding landscape of natural and cultural heritage

Resilient and sustainable communities

A strong connection between people and the landscape

A dynamic and effective AONB partnership

## The Business Plan

This plan will guide the work of the AONB Unit from 2014 - 2017. The actions within it link directly to the implementation of the statutory AONB Management Plan and links are shown against each action.  It is designed to be a rolling 3-year plan, which will be reviewed and updated annually.

The AONB Unit aims to work with the following values at the core of its operation:

We are knowledgeable and passionate about the AONB - its landscape, biodiversity and culture

We care about the environment and sustainability

We work together with others to achieve success

We value people and are approachable and responsive

We communicate clearly and effectively

It should also be recognised that this plan relies on the work of other partner organisations, communities and individuals to achieve the successful delivery of the AONB Management Plan and the long-term vision for the area.

## Strategic Priorities 2014 - 2017

| An outstanding landscape of natural and cultural heritage | Resilient and sustainable rural communities | A strong connection between people and the landscape | A dynamic and effective AONB Partnership |
| --- | --- | --- | --- |
| OL1 Provide and seek advice, training and support to promote sustainable land management practices; helping to safeguard the natural and cultural landscape of the AONB. OL2 Continue a strategic programme of restoration and re-establishment of traditional boundaries (e.g. hedgerows, dry stone walls, railing fences); allied to provision of training opportunities to promote skills associated with these traditional boundaries. OL3 Co-ordinate partner activity in conserving and enhancing biodiversity and in developing better understanding and management of ecosystems services with the AONB. OL4 Work with others, in particular local authorities, to establish development management and other policies/strategies, which result in positive outcomes for the landscape quality of the AONB. | SC1 Continue to support and develop local parish lengthsman schemes within the AONB to assist in the management and maintenance of key community assets. SC2 Support and promote local businesses and products to maintain their viability. SC3 Continue to promote and manage the Sustainable Development Fund; whilst also responding to local community requests for advice on funding, project management and volunteering. SC4 Continue to develop, support and promote local tourism businesses; building on the AONB's reputation as an internationally-recognised destination for sustainable tourism. | PL1 Develop, improve, and promote access and recreational opportunities for a diverse range of people. PL2 Provide high quality information, communications and events to enable people to enjoy and understand the landscape of the AONB and the work of the AONB Partnership. PL3 Support local communities and visitors to conserve, restore, enjoy and learn about the heritage of the AONB, and develop programmes of activity which provide opportunities to engage people with the landscape. | AP1 Work with others to maximise the successful delivery of the AONB Management Plan and effectively monitor progress. AP2 Achieve excellence in the governance and management of the AONB Partnership and Unit, its people and resources; and helping to identify sustainable future funding to support these. |

AONB Unit

CH – Cathy Hopley, Development and Funding Officer

EL – Elliott Lorimer, Principal AONB Officer

HB – Hetty Byrne, Sustainable Tourism & Web Development Officer

MP – Mike Pugh, Business Development Officer

NO – Nick Osborne, Countryside Sites & AONB Manager

SS – Sandra Silk, Projects and Events Officer

Networks for Nectar Project

SR – Sarah Robinson, Project Officer

## Lancashire County Council Environmental Projects and Countryside

DP – Dave Padley, Environmental Projects Officer (covering Craven, Pendle and Ribble Valley)

TW – Tarja Wilson, Environmental Projects Officer (covering Lancaster, Preston and Wyre)

AG – Andrew Greenwood, Head Ranger

An outstanding landscape of natural and cultural heritage (OL)

| OL1 Provide and seek advice, training and support to promote sustainable land management practices; helping to safeguard the natural and cultural landscape of the AONB |
| --- |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| OL1.1 Provide advice, guidance and encouragement to land managers on sustainable land management of the AONB landscape | On-going Regular meetings with local NE Land Management Team Ensure involvement in consultation on NELMS targetting for NW England | On-going Regular meetings with local NE Land Management Team | On-going Regular meetings with local NE Land Management Team | 1.1, 1.2, 2.1 | DP/TW CH/SR/TW/DP/EL |
| OL1.2 Support traditional woodland management skills | 1 traditional woodland management skills course held | 1 traditional woodland management skills course held | 1 traditional woodland management skills course held | 1.3, 2.1 | DP/TW |
| OL1.3 Liaise with woodland planting and management initiatives to encourage and support appropriate woodland extension, creation and management within the AONB landscape | On-going Regular meetings/ liaison with Forestry Commission re: landscape and WGS | On-going Regular meetings/ liaison with Forestry Commission re: landscape and WGS | On-going Regular meetings/ liaison with Forestry Commission re: landscape and WGS | 1.1 | DP/TW/EL |
| OL1.4 Develop design guidance notes for riverside and moorland fencing | Draft guidance notes developed | Guidance notes published |  | 1.1 | DP/EL |
| OL1.4 Engage with newly established River Catchment Partnerships for Ribble, Wyre and Lune to encourage sensitive management of riverbank habitats for biodiversity and landscape. | Regular attendance at RCP meetings Invite RCP members to attend planning and development seminar | Regular attendance at RCP meetings | Regular attendance at RCP meetings | 1.1, 1.2, 1.3, 1.4 | EL/TW/CH/DP |
| OL2 Continue a strategic programme of restoration and re-establishment of traditional boundaries (e.g. hedgerows, dry-stone walls, railing fences); allied to provision of training opportunities to promote traditional rural skills |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| OL2.1 Deliver an annual programme of traditional boundaries projects | At least 3 projects delivered Develop fund-raising plan for traditional boundaries programme (possible inclusion in HLF LPS) | At least 3 projects delivered | At least 3 projects delivered | 1.1, 1.6, 2.1 | DP/TW/EL |
| OL2.2 Promote training opportunities and competitions in hedge-laying and walling (including schools and vocational training) | 2 training opportunities promoted 1 event held | 2 training opportunities promoted 1 event held | 2 training opportunities promoted 1 event held | 1.1, 1.6, 2.1 | DP/TW |

| OL3 Co-ordinate partner activity in conserving and enhancing biodiversity and in developing and better understanding and management of ecosystem services within the AONB |
| --- |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| OL3.1 Hold regular meeting of the AONB Biodiversity Working Group to support the delivery of Biodiversity 2020 'outcomes'. | At least 4 meetings held Annual Delivery Plan developed At least 2 local species recovery plans developed Carry out surveying for agreed priority habitat to help develop opportunity mapping for restoration and creation Carry out ecosystems approach self-assessment toolkit | At least 4 meetings held Annual Delivery Plan reviewed At least 2 local species recovery plans developed | At least 4 meetings held Annual Delivery Plan reviewed At least 2 local species recovery plans developed | 1.2, 1.3, 1.4 | CH/SR EL |
| OL3.2 Utiltise the AONB Peatland Restoration Plan to identify and secure funding for priority peatland and blanket bog restoration works in the AONB. | Attend Lancashire & Pennine Peat Partnership meetings Ensure inclusion AONB priority peatland areas for restoration included in Pennine Peat LIFE+ funding bid One peatland restoration project commmenced (subject to funding) Continue monitoring programme at Bleasdale Restoration Project involving local volunteers | Attend Lancashire & Pennine Peat Partnership meetings One peatland restoration project commmenced (subject to funding) Continue monitoring programme at Bleasdale Restoration Project involving local volunteers | Attend Lancashire & Pennine Peat Partnership meetings One peatland restoration project commmenced (subject to funding) Continue monitoring programme at Bleasdale Restoration Project involving local volunteers | 1.2, 1.3, 2.1 | SR/CH/TW |
| OL3.3 Encourage the restoration of areas of exposed and eroded peat and the conservation and restoration of blanket bog and mosaic of moorland dwarf shrub species, as part of NELMS | Regular meetings with NE HLS advisors and landowners | Regular meetings with NE HLS advisors and landowners | Regular meetings with NE HLS advisors and landowners | 1.2, 1.3, 2.1 | DP/TW |
| OL3.4 Encourage good practice in upland heather burning and alternatives; helping to develop a fire prevention strategy and fire plans for the area | Hold regular AONB-wide fire operations group meetings and exercises | Hold regular AONB-wide fire operations group meetings and exercises Hold Upland Management Seminar, including good practice information on burning | Hold regular AONB-wide fire operations group meetings and exercises | 2.1, 3.2 | NO/AG/DP/TW |
| OL3.5 Delivery of 'Networks for Nectar Project' (successor to Bowland Haytime up to end September 2015) | Carry out monitoring of 'Haytime Project' sites Commence work with farmers, landowners and community groups to develop species-rich grassland small sites projects Hold 5 community engagement events Develop advice and guidance for species-rich grassland managemnt for small sites | Carry out monitoring of 'Haytime Project' sites Conserve, restore and create 10ha of species-rich grassland Hold 5 community engagement events |  | 1.3, 2.3 | SR/CH |
| OL3.6 Support Bowland Land Managers Forum to develop collaborative land management project | Develop and agree priority project for year Identification of potential funding and applications made. | Delivery of project commences, subject to availablity of funding |  | 2.1 | EL |
| OL3.7 Develop proposals for AONB 'Social Forestry' project to involve woodland owners/managers and communities in improving and increasing woodland management, supporting traditional skills and development of local woodfuel economy | Organise visit for local woodland owners/managers and community groups to Arnside and Silverdale AONB 'Social Forestry' and NIA woodlands projects | Establish small-scale pilot 'social forestry' pilot project in AONB. |  | 1.2, 1.3 | TW/DP/EL |
| OL3.8 Support local actions to provide suitable conditions to re-establish hen harrier as a breeding species in the AONB, in line with the government's emerging national species recovery plan | Work with partners to develop local actions with partners to support the re-establishment of breeding hen harrier in the AONB Active participation in the 'Northern England Protected Landscapes Hen Harrier Group' |  |  | 1.4 | EL |
| OL4 Work with others, in particular the local authorities, to establish development management and other policies/strategies, which result in positive outcomes for the landscape quality of the AONB |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| OL4.1 Provide appropriate advice, support and formal responses to development proposals and consultations on policies/strategies that will affect the AONB and its setting (in particular planning applications, local plan consultations and other local, sub-national and national strategies) | Appropriate responses provided | Appropriate responses provided | Appropriate responses provided | 1.1, 1.7 | EL |
| OL4.2 Continue a programme of undergrounding of power lines in the AONB with Electricity Northwest | At least 2 UVA projects delivered | At least 2 UVA projects delivered | At least 2 UVA projects delivered | 1.1, 1.7 | EL/DP/TW |
| OL 4.3 Develop an AONB design guide (based on the Landscape Character Assessment) to ensure development is in keeping with and conserves or enhances landscape character (i.e. in terms of appropriate materials, form, setting, scale etc) | Include as discussion point for planning and development seminar Re-convene working group if agreed | Outline design guide developed Partner consultation held | AONB design guide published Awareness- raising event(s) held | 1.1, 1.7 | EL |
| OL4.4 Liaise with local authority planning officers on relevant AONB planning concerns (landscape character, wind energy, tourism business development, energy efficiency in older buildings) | Planning and development seminar held |  | Planning and development seminar held | 1.1, 1.2, 1.7 | EL |

# Resilient and sustainable rural communities (SC)

| SC1 Continue to support and develop local parish lengthsman schemes within the AONB to assist in the management and maintenance of key community assets |
| --- |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| SC1.1 Support Parish Councils to continue to fund and manage existing lengthsman schemes | AONB grant offer made to Parish Councils/Meetings Develop funding plans with Parish Councils to accommodate reduction in AONB contributions | AONB grant offer made to Parish Councils/Meetings | AONB grant offer made to Parish Councils/Meetings | 2.3, 4.2 | TW/DP |
| SC1.2 Work with Parish Councils to develop best practice (e.g. record-keeping) to help demonstrate best value | Scheme monitoring information received from Parish Councils/Meetings | Scheme monitoring information received from Parish Councils/Meetings | Scheme monitoring information received from Parish Councils/Meetings | 2.3 | TW/DP |

| SC2 Support and promote local businesses and products to maintain their viability |
| --- |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| SC2.1 Support local businesses, via provision of advice, signposting, training (e.g. access for all, business skills, sense of place), networking opportunities and events | One-to-one business advice provided 2 training events provided and evaluated | One-to-one business advice provided 2 training events provided and evaluated | One-to-one business advice provided 2 training events provided and evaluated | 2.2, 2.3, 2.4 | MP/HB |
| SC2.2 Continue to provide support for Bowland Experience Ltd. (BEx) | BEx board meetings held (min. 2/year) Secretariat provided for BEx Regular tourism business bulletin produced and distributed 2 BEx training events held | BEx board meetings held (min. 2/year) Secretariat provided for BEx Regular tourism business bulletin produced and distributed 2 BEx training events held | BEx board meetings held (min. 2/year) Secretariat provided for BEx Regular tourism business bulletin produced and distributed 2 BEx training events held | 2.2, 2.4 | MP/HB/EL |
| SC2.3 Continue to support the development, management and promotion of the Champion Bowland (formerly Bowland Tourism Environment Fund) | Secretariat for Champion Bowland provided Champion Bowland trustees meetings held (min. 2/year) Work with trustees to review Champion Bowland grant-giving (alongside AONB SDF) to maximise effectiveness and value Delivery of AONB 'Farm Visit Transport Fund' through Champion Bowland Launch 50th Anniversary 'visitor-giving' schemes for AONB | Secretariat for Champion Bowland provided Champion Bowland trustees meetings held (min. 2/year) Continue to develop 'visitor-giving' schemes for AONB | Secretariat for Champion Bowland provided Champion Bowland trustees meetings held (min. 2/year) Continue to develop 'visitor-giving' schemes for AONB | 2.2, 2.3, 2.4 | MP/CH CH SS/MP HB/MP |
| SC2.5 Support the continued development of 'Bowland Land Managers Forum' | Regular Forum meetings held Involve Forum members in the development of RDPE/LEADER LAGs, targeting for NELMS and collaborative project development | Regular forum meetings held Forum members involved in relevant RDPE/LEADER LAGs | Regular forum meetings held Forum members involved in relevant RDPE/LEADER LAGs | 2.1, 2.2, 4.2 | EL |
| SC2.6 Raise awareness of the AONB's 50th Anniversary by encouraging partners, communities and business to celebrate and link with the anniversary year. | Organise fund-raising activities to raise £5000 for Champion Bowland Involve businesses and communities in delivery of at least 3 anniversary events/activities |  |  | 2.3 | MP |
| SC3 Continue to promote and manage the Sustainable Development Fund; whilst also responding to local community requests for advice on funding, project management and volunteering |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| SC3.1 Manage the Sustainable Development Fund (SDF) to support appropriate, small-scale projects within the AONB, aiming to increase 'match-funding' from external sources; whilst seeking to promote the fund and individual projects and good practice. | Implement recommendations following review of management arrangements for SDF with Champion Bowland SDF panel meetings held Funded projects complete and return monitoring information, as required SDF Annual Report produced | SDF panel meetings held Funded projects complete and return monitoring information, as required SDF Annual Report produced | SDF panel meetings held Funded projects complete and return monitoring information, as required SDF Annual Report produced | 2.2, 4.2 | CH |
| SC3.2 Provide support to communities seeking project development and funding advice and assistance (e.g. projects to improve provision of rural services, renewable energy projects and local community events) | 10 community groups advised/supported Develop and deliver a programme of awareness-raising activities to promote work of the AONB within communities | 10 community groups advised/supported Continue programme of awareness-raising activities | 10 community groups advised/supported Continue programme of awareness-raising activities | 2.2 | SS/CH HB/SS |
| SC4 Continue to develop, support and promote local tourism businesses; building on the AONB's reputation as an internationally-recognised destination for sustainable tourism |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| SC4.1 Promote the strong 'brand identity' for AONB visitors, working closely with tourism organisations, visitor information centres, businesses and gateway towns | Sense of Place themes and branding used in variety of formats (e.g. website, exhibition panels, pop-up banners) Continue collaboration with Marketing Lancashire, Visit Yorkshire and district tourism partners to effectively promote AONB as a sustainable tourism destination | Sense of Place themes and branding used in variety of formats (e.g. website, exhibition panels, pop-up banners) Continue collaboration with Marketing Lancashire, Visit Yorkshire and district tourism partners to effectively promote AONB as a sustainable tourism destination | Sense of Place themes and branding used in variety of formats (e.g. website, exhibition panels, pop-up banners) Continue collaboration with Marketing Lancashire, Visit Yorkshire and district tourism partners to effectively promote AONB as a sustainable tourism destination | 3.4, 3.5 | HB |
| SC4.2 Support sustainable tourism projects and continue to support GTBS with tourism businesses in the AONB | 4 sustainable tourism projects delivered, (including 'business cluster' projects) 6 GTBS business supported within AONB and 2km buffer | 3 sustainable tourism projects delivered, (including 'business cluster' projects) 6 GTBS businesses supported within AONB and 2km buffer | 3 sustainable tourism projects delivered, (including 'business cluster' projects) 6 GTBS businesses supported within AONB and 2km buffer | 2.2, 2.4 | HB |
| SC4.3 Continue to support and develop appropriate elements of the European Charter for Sustainable Tourism, including support to Charter partners, the Sustainable Tourism Forum, networking within Europarc (particularly within the Atlantic Isles section) | ST Forum held Attend EAI/Europarc meetings, as appropriate AONB JAC decision on continued involvement in EUROPARC Charter for Sustainable Tourism | ST Forum held Attend EAI/Europarc meetings, as appropriate | ST Forum held Attend EAI/Europarc meetings, as appropriate | 2.2, 2.4 | MP/HB |
| SC4.4 Carry out evaluation and monitoring of visitor and tourism enterprise information, in particular visitor pressure, patterns and future markets (including occupancy and satisfaction data) | Evaluate effectiveness of AONB visitor survey and if appropriate develop new approach. Continue tourism business monitoring research on tourism business 'health-check' data | Implement new approach to AONB visitor survey, if carried forward. Continue tourism business monitoring research on tourism business 'health-check' data |  | 2.2, 2.4 | HB/MP |
| SC4.5 Deliver familiarisation visits and study tours for tourism businesses and organisations | One familiarisation visit held | One familiarisation visit held | One familiarisation visit held | 2.2, 2.4 | HB |
| SC4.6 Promote and share good practice of the AONB, as a lead partnership in supporting sustainable tourism within Europe's protected areas | Work with NAAONB & Visit England to develop sustainable tourism collaboration amongst AONBs |  |  | 2.2, 2.4, 4.4 | HB |
| SC4.7 Continue to promote local produce and farming | Manage, review and update local produce database AONB attendance at at least 5 agri. shows/ local produce events for 50th Anniversary 'Bowland Scrapbook' Project (subject to funding) | Manage, review and update local produce database Regularly review AONB future involvement in agri. shows/ local produce events | Manage, review and update local produce database Regularly review AONB future involvement in agri. shows/ local produce events | 2.1, 2.2 | HB |

A strong connection between people and the landscape (PL)

| PL1 Develop, improve and promote access and recreational opportunities for a diverse range of people |
| --- |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| PL1.1 Work in partnership with key stakeholders to maintain and improve access in the wider countryside of the AONB; including support for implementation of PRoW Improvement Plans | Regular meetings of local advisory groups (e.g. Pendle Hill, Upper Hodder) to consider access and recreation issues Active participation in the planned review of the Lancashire RoWIP | Regular meetings of local advisory groups (e.g. Pendle Hill, Upper Hodder) to consider access and recreation issues | Regular meetings of local advisory groups (e.g. Pendle Hill, Upper Hodder) to consider access and recreation issues | 3.1, 3.2, 3.3 | NO/DP/TW/EL |
| PL1.2 Carry out a review of existing AONB promoted routes | Continue to support volunteer monitoring system for existing AONB promoted routes Prioritise promoted routes and rotate twice a year (remove and re-instate where appropriate based on download stats) Annual review of routes completed and acted upon | Continue to support volunteer monitoring system for existing AONB promoted routes Prioritise promoted routes and rotate twice a year (remove and re-instate where appropriate based on download stats) Annual review of routes completed and acted upon | Continue to support volunteer monitoring system for existing AONB promoted routes Prioritise promoted routes and rotate twice a year (remove and re-instate where appropriate based on download stats) Annual review of routes completed and acted upon | 3.1, 3.2, 3.3 | HB/TW/DP |
| PL1.3 Review, rationalise and develop downloadable promoted routes as required | Review and rationalise downloadable promoted route cards 3 new routes cards completed | Review and rationalise downloadable promoted route cards 3 new routes cards completed | Review and rationalise downloadable promoted route cards 3 new routes cards completed | 3.1, 3.2, 3.3 | TW/DP/HB |
| PL1.4 Develop strategic bridleway links within the AONB (e.g. Gisburn Forest to Settle, Lune Valley track and North Lancs Bridleway Phase 2 western sections) | Continued Development of Gisburn Forest to Settle route Hold meeting to discuss development of Lune Valley track between Farleton and Hornby | Commence construction of first sections of GF to S bridleway |  | 3.1, 3.2 | TW/DP |
| PL1.5 Develop 'tramper' access projects | 1 project/route delivered | 1 project/route delivered | 1 project/route delivered | 3.1, 3.2, 3.3 | TW/DP |
| PL1.6 Investigate opportunities to extend access and habitat improvements on Bowland Fells (e.g. flagged paths, stiles, gates to assist in habitat restoration). | Access and habitat improvement project delivered (subject to funding availability) | Access and habitat improvement project delivered (subject to funding availability) | Access and habitat improvement project delivered (subject to funding availability) | 1.3, 3.1, 3.2 | TW/DP/SR |
| PL1.7 Ensure use of appropriate PRoW signposts and access furniture in the AONB | Initial meetings held with PRoW | Guidance note and agreement in place |  | 3.2 | NO/TW/DP |
| PL2 Provide high quality information, communications and events to enable people to enjoy and understand the landscape of the AONB and the work of the AONB partnership |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| PL2.1 Co-ordinate and review Festival Bowland (FB) | Co-ordinate FB Steering Group Evaluation of customer feedback completed (via incentivised postcard scheme) At least 10 FB events organised by AONB Unit Annual review and evaluation of aims and content of FB completed and acted upon | Co-ordinate FB Steering Group Evaluation of customer feedback completed (via incentivised postcard scheme) At least 10 FB events organised by AONB Unit Annual review and evaluation of aims and content of FB completed and acted upon | Co-ordinate FB Steering Group Evaluation of customer feedback completed (via incentivised postcard scheme) At least 10 FB events organised by AONB Unit Annual review and evaluation of aims and content of FB completed and acted upon | 3.4, 3.5 | SS |
| PL2.2 Publicise Festival Bowland programme | 50th Anniversary FB brochure produced Monthly FB events posters produced and distributed 10 press releases/year produced to promote FB events Update Google calendar and LOIS database with FB events | FB brochure produced Monthly FB events posters produced and distributed 10 press releases/year produced to promote FB events Update Google calendar and LOIS database with FB events | FB brochure produced Monthly FB events posters produced and distributed 10 press releases/year produced to promote FB events Update Google calendar and LOIS database with FB events | 3.4, 3.6 | SS |

| PL2.3 Support and promote external events and tourism businessses that help to deliver AONB objectives | Agree new arrangements for AONB listings of accomodation, 'eateries', attractions and activities listings with Marketing Lancashiret through LOIS Maintain LOIS database for partner-led events and accommodation | Maintain LOIS database for partner-led events and accommodation | Maintain LOIS database for partner-led events and accommodation | 3.4, 3.6 | HB |
| --- | --- | --- | --- | --- | --- |
| PL2.4 Management and implementation of the Forest of Bowland AONB brand and graphic standards | Review current printed publications and update/rationalise as appropriate Develop AONB 'wildlife' leaflet to replace current 'birding' leaflet Training on branding guidelines for partner organisations and businesses, where required Create web-friendly downloadable leaflets when producing new print and add guidelines to graphic standards Review communications strategy | Review current printed publications and update/rationalise as appropriate Training on branding guidelines for partner organisations and businesses, where required Create web-friendly downloadable leaflets when producing new print and add guidelines to graphic standards | Review current printed publications and update/rationalise as appropriate | 3.4, 3.5, 4.4 | HB/SS |
| PL2.5 Update and replace AONB boundary signs at key visitor 'gateways' to the AONB | 2 boundary signs replaced | 2 boundary signs replaced (if funding allows) | 2 boundary signs replaced (if funding allows) | 2.3, 3.5 | DP/EL |
| PL2.6 Manage and maintain 'Take One Media' brochure and leaflet distribution service | Periodic review of Take One Media reports carried out | Periodic review of Take One Media reports carried out | Periodic review of Take One Media reports carried out | 3.4, 4.4 | HB |
| PL2.7 Regularly review and update the content of AONB website, in line with AONB Management Plan objectives and actions | Periodic review and update of route downloads completed Website data analysis completed and disseminated | Periodic review and update of route downloads completed Website data analysis completed and disseminated | Periodic review and update of route downloads completed Website data analysis completed and disseminated | 3.4, 3.5, 4.4 | HB |
| PL2.8 Review design of AONB website | Web design support contracted Web design 'refresh' completed, including mobile-friendly companion site. |  |  | 3.4, 3.5, 4.4 | HB |
| PL2.9 Research good practice in use of emerging technology to help interpret and promote the AONB | Continue to develop use of social media to promote AONB (e.g. Twitter, Facebook) Develop 'apps' to help widen audience for AONB generally and for specific project information and interpretation, where appropriate | Continue to develop use of social media to promote AONB (e.g. Twitter, Facebook) Develop 'apps' to help widen audience for AONB generally and for specific project information and interpretation, where appropriate | Continue to develop use of social media to promote AONB (e.g. Twitter, Facebook) Develop 'apps' to help widen audience for AONB generally and for specific project information and interpretation, where appropriate | 3.4, 4.4 | HB |
| PL2.10 Source and promote newsworthy stories that promote the AONB and work of the partnership | Quarterly e-bulletin produced and promoted Contacts maintained within local, regional and national media 6 AONB press releases per year produced | Quarterly e-bulletin produced and promoted Contacts maintained within local, regional and national media 6 AONB press releases per year produced | Quarterly e-bulletin produced and promoted Contacts maintained within local, regional and national media 6 AONB press releases per year produced | 3.4, 4.4 | HB/SS |
| PL3 Support local communities and visitors to conserve, restore, enjoy and learn about the heritage of the AONB; and develop programmes of activity which provide opportunities to engage people with the landscape |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| PL3.1 Support the development of the 'Friends of Bowland', to co-ordinate and support volunteers for the AONB | AONB representative attend 'Friends' committee meetings as advisor Assist 'Friends' in development of events/activities programmes Develop at least one joint project/event with 'Friends' | AONB representative attend 'Friends' committee meetings as advisor Assist 'Friends' in development of events/activities programmes Develop at least one joint project/event with 'Friends' | AONB representative attend 'Friends' committee meetings as advisor Assist 'Friends' in development of events/activities programmes Develop at least one joint project/event with 'Friends' | 2.3 | CH |
| PL3.2 Identify funds and partners to help deliver AONB-wide programmes of activity to research, conserve, enhance and interpret the landscape heritage of the AONB | Prioritise and develop Heritage Lottery Fund bids to support and deliver landscape heritage projects, inc. Landscape Partnership Scheme (LPS) Development of Stage 1 bid ot HLF LPS Deliver AONB 50th anniversary 'Bowland Scrapbook' Project, (subject to HLF funding application) | Commence HLF LPS development phase if approved. | Submit HLF LPS Stage 2 bid Commence delivery of HLF LPS | 1.1, 1.2, 1.3, 1.5, 1.6, 2.1, 2.2, 2.3, 2.4, 3.1, 3.3, 3.5 | CH |
| PL3.3 Produce on-line resources for use by schools and other groups for AONB educational farm visits | Review uptake of online educational resources and improve/amend as appropriate Review work carried out with schools on using AONB for fieldwork and outdoor education for 14-18 year olds in the AONB, and develop further if appropriate | Review uptake of online educational resources and improve/amend as appropriate |  | 3.4, 3.6, 4.4 | SS/CH |
| PL3.4 Continue development of community outreach activities to encourage new audiences that traditionally do not know about or visit the AONB | Review pilot 'Bowland Outreach' project Funding secured for continuation of community outreach activities, if agreed following review | Deliver community outreach activities |  | 3.6 | SS |
| PL3.5 Hold a series of special events and activities celebrating the 50th Anniversary of the designation of the Forest of Bowland AONB | Launch event held on designation date (10th February 2014) Arts 2014 project delivered AONB 50th Anniversary Awards Clitheroe Real Ale Festival and special Bowland Brewery 'AONB 50th Beer' visitor-giving scheme Closing Gala event held | Arts 2014 legacy project delivered (subject to funding) |  | 2.2, 2.3, 2.4 | All |

# A dynamic and effective AONB partnership (AP)

| AP1 Work with others to maximise the successful delivery of the AONB Management Plan and effectively monitor progress |
| --- |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| AP1.1 Participate in a range of fora and networks to represent AONB interests (e.g. Local Nature Partnerships, Local Enterprise Partnerships, RDPE/LEADER LAGs) | On-going | On-going | On-going | 4.1, 4.4 | All |
| AP1.2 Review the AONB Management Plan, in accordance with national guidance | AONB Management Plan adopted by local authorities and published |  |  | 4.1 | EL |
| AP1.3 Ensure effective and inclusive consultation is carried out on all major AONB strategies and activity | On-going | On-going | On-going | 2.3, 4.4 | EL |
| AP1.4 Manage and promote the interactive management plan (IMP) to ensure regular monitoring of partnership delivery of actions | Implement review of IMP functionality and reporting IMP updated by Unit and partners | IMP updated by Unit and partners | IMP updated by Unit and partners | 4.1, 4.4 | HB/EL/CH |
| AP1.5 Produce a clear and concise AONB Annual Report | Annual Report produced | Annual Report produced | Annual Report produced | 2.2, 3.4, 4.4 | SS |
| AP1.6 Produce quarterly progress reports on business plan delivery | Quarterly reports produced | Quarterly reports produced | Quarterly reports produced | 4.4 | EL |
| AP1.7 Develop a 'State of the AONB' Report to monitor and evaluate landscape change within the AONB, monitor delivery of the AONB Partnership outcomes and provide a sound evidence base for future project development and funding bids | Agree priority base-line datasets and develop indicators Commence data collation and produce early draft report | Produce 'State of the AONB Report' |  | 4.3 | CH |
| AP1.8 Work with, and support National Association for AONBs (NAAONB) and other protected areas to share best practice and strengthen the status of AONBs locally and nationally | NAAONB and Northern Group events attended Support and assist in organisations of NAAONB Annual Conference and Northern Group visit to AONB in 2014 Responses made to NAAONB information and consultation requests, where appropriate | NAAONB and Northern Group events attended Responses made to NAAONB information and consultation requests, where appropriate | NAAONB and Northern Group events attended Responses made to NAAONB information and consultation requests, where appropriate | 4.4 | All |
| AP1.9 Support and maintain co-ordinated delivery of services and projects in the AONB in partnership with local authority countryside and environmental projects teams | LCC E&C Projects staff attend AONB team meetings, where appropriate Periodic meetings held with local authority and United Utilities countryside staff | LCC E&C Projects staff attend AONB team meetings, where appropriate Periodic meetings held with local authority and United Utilities countryside staff | LCC E&C Projects staff attend AONB team meetings, where appropriate Periodic meetings held with local authority and United Utilities countryside staff | 4.1, 4.4 | EL/NO |
| AP2 Achieve excellence in the governance and management of the AONB Partnership and Unit, its people and resources; and helping to identify sustainable future funding to support these. |
| We will: | 2014/15 | 2015/16 | 2016/17 | AONB MP 2014 – 2019 Objectives | Staff lead(s) |
| AP2.1Ensure effective and productive functioning of AONB Joint Advisory Committee and its working groups, with agreed terms of reference | 2 JAC meetings, 3 to 4 partnership funders group and regular working group meetings held | 2 JAC meetings, 3 to 4 partnership funders group and regular working group meetings held | 2 JAC meetings, 3 to 4 partnership funders group and regular working group meetings held | 4.1 | EL |
| AP2.2 Review membership of the AONB Joint Advisory Committee for non-statutory organisations and non-funding partners | Review of current JAC membership for non-statutory organisations and non-funding partners completed Develop induction information for new JAC members Investigate potential for JAC members to act as porfolio-holders and AONB champions |  |  | 4.1 | CH/EL |
| AP2.2 Hold regular meetings and correspondence with AONB funding partners to ensure AONB Partnership and Unit are delivering against partners' key corporate objectives | Regular Partnership Funders Group meetings held | Regular Partnership Funders Group meetings held | Regular Partnership Funders Group meetings held | 4.1 | EL |
| AP2.3 Continue to support and liaise with NAAONB (as part of the tri-partite agreement with Defra and Natural England) to lobby for retention of secure, long-term funding arrangements for AONBs | NAAONB meetings, seminars and conferences attended, where appropriate | NAAONB meetings, seminars and conferences attended, where appropriate | NAAONB meetings, seminars and conferences attended, where appropriate | 4.4 | EL/NO |
| AP2.4 Ensure that 'Memorandum of Agreement' (MoA) is in place between Defra and AONB funding partners |  | New MoA signed by all partners |  | 4.1, 4.4 | NO/EL |
| AP2.5 Develop a fund-raising strategy for the AONB partnership | Monitor and update fund-raising strategy implementation on-going | Review strategy and continue implementation, as appropriate |  | 4.2 | CH |
| AP2.6 Aim for excellence in management of the AONB Unit | Productive fortnightly team meetings, 1-to-1 meetings, employee PDRs and team building activities carried out | Productive fortnightly team meetings, 1-to-1 meetings, employee PDRs and team building activities carried out | Productive fortnightly team meetings, 1-to-1 meetings, employee PDRs and team building activities carried out | 4.1 | NO/EL |
| AP2.7 Provide structured training opportunities to AONB Unit and representatives | Staff training identified and attended | Staff training identified and attended | Staff training identified and attended | 4.1 | NO/EL |
| AP2.8 Annually review and update three-year AONB Unit business plan | Annual review and update completed | Annual review and update completed | Annual review and update completed | 4.1 | EL |
| AP2.9 Promote good practice in project management (incorporating best value, monitoring and evaluation, sustainability and involving volunteers) | Staff training identified and attended. | Staff training identified and attended. | Staff training identified and attended. | 4.1 | NO/EL |
| AP2.10 Implement AONB Unit environmental policy and action plan | Review AONB Unit Environmental Policy, with new actions and targets set Carbon reduction targets achieved (including move to new premises) | Review AONB Unit Environmental Policy, with new actions and targets set Carbon reduction targets achieved (including move to new premises) | Review AONB Unit Environmental Policy, with new actions and targets set Carbon reduction targets achieved (including move to new premises) | 4.1 | CH |

# Text boxes

AONB Unit Business Plan 2014 – 2017

DRAFT (April 2014)

AONB Unit

October 2011

Authors Name Authors Title

Date

Authors Name Authors Title

Date

Authors Name Authors Title

Date