Appendix 'A'

Lancashire Adult Learning Post Inspection Action Plan

The focus of activity for Lancashire Adult Learning in 2014/15 is to address the identified areas for improvement arising from the Ofsted Inspection November 2014.

Key Ofsted Recommendations:

Objective 1    Ensure clarity of roles and responsibilities within the senior leadership team impacts upon effective quality improvement.

Objective 2   Improve the governance of the provision by introducing frequent scheduled opportunities for governors to support and to hold managers to account for delivering high quality in all aspects of learners’ experience and achievement.

Objective 3    Ensure the rapid improvement of the quality of provision through accurate self-assessment through thorough and frequent monitoring of challenging and measurable quality improvement plans which contain clear targets and milestones.

Objective 4    Improve the quality of teaching, learning and assessment to ensure that all learners benefit from high standards of teaching and learning.

Objective 5   Improve the use of key data sets to manage and monitor the provision.

Objective 6    Address declining success on long qualifications.

Objective 7    Address declining success on short qualifications.

Objective 8    Address success on some workplace programmes.

Objective 9    Address success on level 1 qualifications.

Objective 10   Address declining success on some level 2 qualifications.

Objective 11   Address declining success on functional skills qualifications.

Objective 12   Ensure that initial assessment collects key information on learners’ starting points and aspirations and all tutors are skilled in the setting and use of clear, challenging and achievable targets for learners on non-accredited courses.

Objective 13   Ensure the comprehensive collation of data on community learning programmes to measure the sustainable impact on communities.

Objective 14   Ensure the systematic collation of data on employability/work clubs to measure the impact on unemployed learners.

Objective 15   Better support the acquisition of English and mathematics in occupational teaching by ensuring that learners understand their relevance and value.

Objective 16   Ensure learners receive effective support to overcome any barriers to their progress and achievement.

Objective 17   Improve the collection of learner feedback.

Objective 18   Develop learning activities to widen learners’ perceptions of equality and diversity and celebrate differences.

Objective 19   Ensure safeguarding procedures are consistently applied across the provision and in particular address the needs of young learners.

Post Inspection Action Plan 2014/15

| Objective (Number) | Action | Expected Outcome | Target Date | Milestones | Responsibility | Progress and Impact |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Appoint interim Principal to lead changes and clarify roles and responsibilities. Interim Deputy to lead quality improvement Review existing leadership structure and redundancy arrangements Evaluate capacity of existing team to implement rapid quality improvement Design new leadership structure to secure clarity of ownership of responsibility Existing staff extensions or redundancy agreements finalised Appoint permanent senior post holders and senior leadership team New senior leadership structure agreed with clear job descriptions and key accountabilities. | Interim Principal in post Interim Deputy in post New leadership team appointed | Jan 1 2015 Jan 1 2015 30 Jan 2015 redundancy and extensions of existing leadership confirmed and agreed 1 June 2015 new leadership team appointed | TO BE INSERTED | Governing Board Interim Principal | January 2015 Interim Principal appointed and Interim Deputy Principal appointed |
| 2. | Establish and implement Governing Body. Governor attendance at all key external briefings and training events. Governor representation and attendance at external OTL Up-skilling event. Identify ‘Link Governors’ to specific curriculum areas. Key governor involvement in self-assessment process. Introduce Governor Data Set Reports to ensure all governors are kept informed of progress towards achieving the Strategic QIP. Develop and introduce training opportunities for Governors to keep abreast of reforms | Governing Body established. Governing Body has a detailed knowledge of the organisation and holds the organisation to account Governing Body is active in setting the strategic direction of the organisation | 30 Jan May 2015 July 2015 | TO BE INSERTED | Interim Principal | 8 January 2015 Chair and Vice Chair identified and board members drafted. Interim Clerk appointed. Date scheduled for first meeting. NLG identified to undertake governance training for new board |
| 3. | Review self-assessment tool against the Common Inspection framework. All staff teams trained on self-assessment Use Primary Source Data in order to accurately assess outcomes for learners. Identify and introduce key information sources to inform self-assessment process and enable accurate measurement of provision. Source and introduce External validation of subject self-assessments. Introduce whole organisation quality cycle identifying key quality measures, interventions and monitoring processes through the year. Introduce the Curriculum Audit Process on all SRIs to support Quality Improvements. | Revised self-assessment tool in place. Staff understand how to apply judgments, can identify the supporting evidence to accurately grade curriculum areas Successful external validation of self-assessment by end March 2015. Quality Cycle Implemented and understood by all staff. Impact of Curriculum Audits measured against improvements in success of SRIs | February 2015. March 2015. . May 2015 June 2015 | i.a Draft self -assessment tool agreed by SMT and shared with CMs and ACMs. By January 2015 ii.a Introduce Quality Roadshow for All Staff. 1st to cover briefing on PIAP. ii.b Initial training on self-assessment completed by CMs, ACMs. ii.c CMs and ACMs coached on completing self-assessment for curriculum areas by external consultant and Quality Manager. By end February 2015. iii.a CMs and ACMs have access to Pro-achieve. iii.b MIS to produce data tables within self-assessment tool. By February 2015 iv.a Quality Manager and external consultant support each curriculum team to identify key information sources specific to their provision. By March 2015 v. a Book external by February 2015 vi.a Draft Quality Cycle produced and shared with SMT vi.b All staff briefings on Quality Cycle delivered by March 2015 vii a. Curriculum audit tool shared and agreed with SMT by March 2015. vii.b curriculum audit shared with staff in quality Briefings by end March 2015. Curriculum Audit carried out on SRIs by April 2015. | Interim Deputy | Jan 8 2015 Self- assessment tool revised. External trainer booked. |
| 4. | Review the core observation team. Lesson observation up-skilling for all members of the core observation team. Review current OTL processes and evaluate effectiveness in improving teaching, learning and assessment Introduce whole organisation CPD with a focus on developing and sharing best practice both internally and externally. | Core Team reviewed, trained and in place Successful external validation of Observation Profile. CPD Programme in place which identifies good practice to be shared across the organisation | June 2015 | i.a Core observation team identified and agreed by Jan 2015. ii.a Core team trained on OTL by February 2015. ii.b OTL plan in place to ensure all core team undertake dual and mentored lesson observations by end Feb 2015 ii.c Dual and mentored OTL completed by end April 2015. ii.d Internal moderating activities begin February and completed by end April 2015. iii.a Revised OTL process presented to SMT by end Jan 2015. ii.b Revised OTL process introduced to core observation team and used as part of OTL Training by Feb 2015. iii.c Internal moderation activity of core team observations completed by April 2015 iii.d External validation and review of OTL process completed by May 2015. iv.a CPD Plan drafted to include from ‘areas for improvement on OTL ‘to date’ (January 2015); key goals; SRIs; inspection report. By March 2015 iv.b Seek external best practice models from outstanding providers by end March 2015. iv.c Identify best practice from revised OTL process by end April 2015. | Interim Deputy APs Curriculum | 8 Jan Observation Team reviewed |
| 5. | Introduce accessible key data sets for weekly monitoring –for Curriculum Managers. Introduce data sets for use by learning support staff and teaching staff to enable record, track and monitor progress of learners in receipt of support. Develop and introduce key data sets for the Governing Body. Implement staff training for Team Leaders, Assistant Curriculum Managers and Advanced Practitioners on use of Primary Data Sets. | Accurate monitoring of learner retention and progress using common key data sets. Improvement in headline progress and achievement of learners (see Obs 6, 7, 8, 10, 11). Accessible data sets for Governors introduced and used as monitoring tool | June 2015 | i.a Trial data sets using existing course files for CPR Panel 1 by January 2015. i.b Review course file in light of data reports for CPR ic. Procure management information system by end Feb 2015. i.d Appoint external MIS consultant to work with curriculum teams and MIS. i.e Identify common reporting systems developed at NCC which can be migrated to LAL system. i.f Procure i.g Trial patch of software onto existing Goldmine data by Jan 2015. i.h Procure Pro-achieve. i.I Migrate 5 year data sets from Goldmine to Pro-achieve by Jan 2015. i.j CMs and ACMs access pro-achieve on desktops by February 2015. ii.a Procure Spirals software by Feb 2015 iii.a Appoint external MIS consultant to work with SMT and MIS. iii.b identify parameters for data dashboard reporting by end Feb 2015. iii.c iv.a Staff training on pro-achieve commence Feb 2015. iv.b Staff training on EBS data reporting sets by March 2015. | AP Business Support | 8 Jan 2015 Parameters of reports agreed and set. Successful completion of trial 'patch' on Primary Source Data; APs Curriculum can access data and have shared with teams. |
| 6, 7, 8, 10,11 | Revise bespoke monitoring reports and ensure weekly accessibility for APs Curriculum, CMs, ACMs, Adv.Ps and Vocational Team Leaders. Introduce monthly curriculum performance reporting against targets for all SRIs. Introduce accessible key data sets through development of MIS for all teachers. Ensure all ACMs and Adv.Ps access and use Primary Source Data Sets. Identify and share with staff clear lines of reporting and accountability. Review exams process to ensure timely summative assessment supports achievement of Functional Skills. | Success on all long qualifications (Overall) from 84.8% in 2013/14 to 92% (Nat Ave. 87.6%) Success on all short programmes (headline) 94% (Nat Ave.87.4%) Success on L2 Teaching and Learning (Award in Support Work in Schools) from 71.1% in 2013/14 to 83% (Nat. Ave 81.3%) Success on L2 Health & Social Care (Certificate in Preparing to Work in Adult Social Care) from 66.7% in 2013/14 to 85% (Provider Group Ave 78.4% Level 2 Award in Counselling Concepts from 75% in 2013/14 to 88% (Nat Ave 85.3%) Level 2 Certificate in Preparing to work in Adult Social Care from 66.7% in 2013/14 to 88%%% (Nat Ave 86.1%) Level 2 Award in Support Work in Schools from 71.1% in 2013/14 to 85% (Nat Ave 81.3%) GCSE Science from 78.6% in 2013/14 to 82% (Nat Ave. 80.2%) GCSE Mathematics 78.9% in 2013/14 to 83% (Nat Ave. 78.9%) Timely Success for Level 1 Functional Skills English from 67.4%% in 2013/13 to 71% (Nat Ave 65.9%) Timely success for Level 1 Functional Skills Maths from 67.2% in 2013/14 to 73% (Provider Group Ave 67.6%%) Timely success for Level 2 Functional Skills Maths from 63.8% in 2013/14 to 69% (Provider group Ave 67.5%) | Achieve target success (Overall) July 2015 | i.a Review course file in light of data reports for CPR ib. Procure management information system by end Feb 2015. i.c Appoint external MIS consultant to work with curriculum teams and MIS. i.e Introduce new retention reports aligned to curriculum teams ACMs and CMs by end Feb 2015. ii.a Review SMT agenda to incorporate monthly item against SRIs by Feb 2015 iii.a Enable key data sets to be accessed via Moodle by March 2015. iv.a Trial patch of software onto existing Goldmine data by Jan 2015. iv.b Procure Pro-achieve. i.v.c Migrate 5 year data sets from Goldmine to Pro-achieve by Jan 2015. iv.d CMs and ACMs access pro-achieve on desktops by February 2015. v.a Review curriculum structure to ensure all staff understand reporting responsibilities by course by Feb 2015. vi.a Review process for entry best suits in-year summative assessment by end Feb 2015. vi.b communicate any revised procedure to Business Support staff and teaching teams via team briefings. | APs Curriculum AP Business Support | Jan 8 2015 Weekly retention reports agreed and actioned for w/c 19 Jan. Successful trial of ‘patch’ on ILR enables APs to view primary source data and share with CMs. SRIs identified through QSR reports and current potential at risk. SRI meetings attendance by APs, CMs and ACMs. Procurement agreed for new primary source data software collection booked w/c 19 Jan mandatory |
| 9. | Produce key data sets to ensure appropriate monitoring of identified cohorts Review initial advice and guidance on all level 1 programmes Prompt interventions for learners at risk Review impact of direct learner support for those learners on level 1 programmes. | Achieve headline success on level 1 Certificate from 90.8% in 2013/14 95% (Nat Ave. 91.8% Achieve headline success on Level 1 Award from 88.1% in 2013/14 to 93% (Nat Ave. 89.7%) Award in Number Entry Level 3 from 65.2% in 2013/14 to 89% (Nat Ave 82.1%) Level 1 Award in Reading/Writing/speaking and Listening from 65.9% in 2013/14 to 90% (Nat Ave 86.8%) | July 2015 | i.a Procure spirals software to monitor and track learners in receipt of support by Feb 2015. ii.a Clarify roles and responsibilities of staff involved in IAG by end Feb 2015. ii.b Staff involved in IAG complete training by march 2015. iii.a. Retention reports identify learners at risk in place by end Feb 2015. iii.b Review procedures for flagging learerns at risk wth support team by end Feb 2015. iv.a produce tracking report within Spirals to capture achievement of learner in receipt of support. iv.b communicate the impact of learning support to curse teams via the self-assessment process by June 2015. | AP Community Learning AP Business Support | Jan 8 2015 Weekly retention reports agreed and actioned for w/c 19 Jan. Successful trial of ‘patch’ on ILR enables APs to view primary source data and share with CMs. SRIs identified through QSR reports and current potential at risk. SRI meetings booked w/c 19 Jan mandatory attendance by APs, CMs and ACMs. Procurement agreed for new primary source data software collection. |
| 12. | All staff involvement in RARPA training. Introduce weekly monitoring within teams of learner’s progress towards timely achievement of individual targets. Review verification process and recording of learner achievement. | All learners access and complete initial assessment. Individual Learning Plans in place on all community and employability programmes. Regular and systematic monitoring and recording in place Validation of achievement towards targets. | April 2015 | i.a teaching staff teaching on community learning programmes complete RARPA training by Jan 2015. i.b Moderation and validation calendar for RARPA introduced by end January 2015 i.c Follow up audit of ILPs completed by end March 2015. ii.a Standard agenda item on AP Curriculum Team Meetings to monitor learner progress and achievement by course by Feb 2015. iii.a AP and Curriculum Team review current recording on registers of achievement by end Feb. iii.b Clear recording and reporting of achievement procedures agreed and communicated to Business Support team and curriculum teams by end Feb 2015. | AP Community Learning | Dec 2014 Exemplar template for RARPA requirements developed. Training for ACMs and APs completed. w/c 5 Jan 2015 Minimum standards disseminated to tutors and followed up in team meetings. |
| 13, 14 | Exit interviews to be completed as part of summative assessment on programmes. Follow up destination survey to be completed to measure sustainability of positive destinations. Review curriculum offer and appropriateness for value to learner progress. | 95% of known learner destinations on community learning and employability programmes 75% of learners achieve positive destinations on work club programmes. Curriculum offer review and completed. | February 2015 and on-going thereafter June 2015 Curriculum offer revised and Business Planned June 2015 Impact measured and informs Business Planning. | TO BE INSERTED LC | AP Curriculum AP Business Support | Revised ILP to capture destination Revised subcontracting information to capture impact on local communities. Revised course planning pro-forma to capture impact on community learning. Creation of interface in MIS commenced to collate destination information. |
| 15. | Introduce a whole organisation strategy for the English and mathematics. Focus activities by Advanced Practitioners to share best practice from the national Enhancement Programme. Targeted staff development programme implemented to include focus on developing English and maths skills. Audit of schemes of work and lesson plans to ensure opportunities for reinforcement of English and mathematics are identified and delivered. Introduce Learner Voice activities to measure the impact above actions. | Audit of on learner work demonstrates feedback on errors are accurately identified, understood by the learner and acted upon. Revised OTL which includes focus on identifying and sharing good practice in developing English and mathematics Learner feedback in occupational areas demonstrates they have a good understanding on the relevance of developing English and mathematics to support life chances | 23 Feb 2015. Batch Audit of learner work completed 30 Feb 2015. OTL in place and operational. Revised tool for collecting data from OTL operational. 30 March 2015. Completion of first round of learner feedback from occupational lessons completed. | TO BE INSERTED LR | AP Adult Skills | 8 January 2015 Internal Lead Practitioners identified and Training planned w/c 26 Jan. |
| 16. | Review process for identifying and timely support of learners at risk. Introduce data sets for monitoring the progress of learners identified as at risk and in receipt of support. Include specific LST/teachers training within CPD Plan. Introduce monitoring of in-class support within OTL Process. | Retention of identified groups of learners at risk improved; Level 1 Award retention 96% (Nat Ave 95.2%) | June 2015 | TO BE INSERTED LC | APs Curriculum | Dec 2014 Risk assessment procedure flags individual need prior to start of programme. Questions on enrolment form ensures learners are pre-screened for support Jan 8 2015 Procurement commenced for software to track progress of learners at risk |
| 17. | Revise and implement learner voice process. Increase the number of learner feedback. Measure the impact of learner feedback on improvement in provision. | Revised Learner Voice Process in place. Learner Voice can be accurately measured and positively impacts upon the provision. | Feb 2015 June 2015 and on-going Learner voice activities carried out across the provision; 'you said we did' actions identified and impact measured | TO BE INSERTED KN | APs Curriculum AP Business Support |  |
| 18. | Establish a service wide E & D Group for reporting purposes. Delver mandatory training to update quality and diversity standards. Monitor planning documentation to identify impact of training. Identify tutors who need additional support in the promotion and planning of E & D in lessons. | E & D is positively identified through the OTL process E & D is positively identified through learner feedback. Positive promotion of difference is recognised and shared with learners. All teachers and support staff complete mandatory training | April 2015 June 2015 January 2015. Teachers and support staff complete mandatory training | TO BE INSERTED LC | . APs Curriculum | January 2015 Service wide group established. Mandatory training planned w/c 19 January |
| 19. | Rapidly implement the Safeguarding Action Plan. Central collation of risk assessments on vulnerable learners. | Action plan implemented Safeguarding is positively identified through the OTL process and/or curriculum audits. Safeguarding is positively identified through learner feedback. Central register compiled on all vulnerable learners and is shared with appropriate staff. | 30 Jan 2015 April 2015 March 2015 and on-going | TO BE INSERTED LC | AP Community | January 2015 LCC Professional Boundaries inc e-safety and use of social media sourced and cascaded to staff. CPD Proposal drafted for SMT. Links made with external agencies to deliver training t address radicalisation/extremism agenda. e-safety staff training planned for March 2015. Information governance training completed by all staff (Dec 2014). Safeguarding tracking sheet updated to capture bullying and harassment. Links made with LCC LADO. |