| Date | 13th April 2015 |
| --- | --- |
| To | Transport for Lancashire (TfL) |
| From | Jacobs |
| Subject | Blackburn to Manchester Rail Corridor Improvement Scheme |

Introduction

The purpose of the review is to inform TfL’s recommendation on whether the Blackburn to Manchester Rail Corridor Improvement Scheme should be granted Full Approval status at the LEP Board meeting on the 21st April 2015. This would subsequently enable the scheme to draw down Growth Deal funds and proceed to implementation.

Scheme Milestones

Table 1 summarises the key milestones in the approval process for the scheme.

| Date | Task |
| --- | --- |
| December 2014 | BwDBC completed the Outline Business Case for the scheme. |
| February 2015 | Jacobs undertook a comprehensive review of the scheme’s Outline Business Case. |
| February 2015 | Scheme granted Conditional Approval status at the LEP Board meeting on the 10th February 2015. |
| February / March 2015 | BwDBC updated the Outline Business Case to be a Full Business Case. |
| March 2015 | Jacobs reviewed the Full Business Case for the scheme. |
| April 2015 | Scheme Seeking Full Approval at the LEP Board meeting on the 21st April 2015. |

Table 1: Key Milestones

Methodology

The scheme’s Outline Business Case (December 2014) was previously reviewed and evaluated against the Department for Transport’s (DfT) guidance on The Transport Business Cases (January 2013). The business case was also assessed to ensure consistency with the Lancashire Enterprise Partnership’s Accountability Framework.

Jacobs have subsequently reviewed the scheme’s Full Business Case (March 2015) to ensure that each of the conditions that were placed on the scheme, when it was granted Conditional Approval status, have been met.

The review has also ensured that each of the recommendations that were previously suggested have been incorporated into the Full Business Case update.

As part of the review process, Jacobs have actively engaged with the scheme promoter (BwDBC) in order to agree on viable and proportionate solutions to any key issues.

Conclusions

The Blackburn to Manchester Rail Corridor Improvement Scheme should be granted Full Approval status and subsequently enable the scheme to proceed to implementation.

The table below summarises how each of the six conditions previously placed on the scheme have been resolved.

| Ref | Condition of Scheme (Feb 15) | Resolution |
| --- | --- | --- |
| 1 | Confirmation is received (when the ITT for the new Northern Franchise is publically available) that the Manchester to Blackburn service is to be included as part of the baseline specification for the next Northern Franchise. | The Northern Invitation To Tender (ITT) document was published by the DfT on the 27th February 2015. The Train Service Requirement (TSR) table specifies that the winning bidder must operate a half hourly service, between Blackburn and Manchester, throughout the off peak period (i.e. 12 trains between 10:00-16:00). |
| 2 | Confirmation is received (when the ITT for the new Northern Franchise is publically available) that the operational costs of the Manchester to Blackburn service will be funded as part of the next Northern Franchise, thus removing the need for BwDBC to subside the scheme. |  |
| 3 | The scheme BCR is currently 1.47 (based on latest guidance), rising to 2.25 with the inclusion of wider economic benefits. In accordance with the LEP’s Accountability Framework, the scheme should deliver high VfM (BCR >2 when incorporating both traditional and wider economic benefits), once the target scheme costs are confirmed and with optimism bias applied at 6% (consistent with the DfT’s Rail Appraisal guidance for a scheme at GRIP Stage 5). This is considered the key risk associated with the scheme being granted Full Approval. | The updated Economic Case states that the Benefit to Cost Ratio (BCR) for the scheme is now 4.63. This rises to 6.93 when the full wider economic impacts of the scheme are taken into account. The main reason for the BCR increasing is due to the removal of operating costs (as they will now be met by the TOC). Optimism Bias has been correctly applied at 6%, in line with guidance. |
| 4 | The results of a more detailed environmental assessment (including consideration of noise and air quality) demonstrate that the scheme does not have a significant detrimental impact upon any sensitive receptors. | An Environmental Impact Appraisal has been undertaken which concluded that there are no significant adverse environmental impacts associated with the scheme. Appropriate mitigation has been identified which should be incorporated into the scheme design and contractor input. |
| 5 | The scheme opening year being confirmed, and if necessary the Business Case (including the economic assessment) being updated accordingly. | The Full Business Case (including the economic assessment) has been updated to reflect a scheme Opening Year of 2017, which is the back stop date for introduction of the additional services. |
| 6 | Clarification sought that any cost overspends will be met by BwDBC (in accordance with the LEP’s Accountability Framework) to ensure that the scheme will be delivered in its entirety. | An updated Section 151 Officer Letter (reflecting the revised scheme costs) has been appended to the Full Business Case |

Table 2: Resolved Conditions

In addition, each of the recommendations that were previously raised in the Red Amber Green (RAG) analysis (as part of the Outline Business Case review) have now been addressed.

Recommendations

The Blackburn to Manchester Rail Corridor Improvement Scheme should be granted Full Approval status, thus enabling the scheme to draw down Growth Deal funds and proceed to implementation.

To ensure the benefits of the scheme are maximised, it is critical that BwDBC, LCC and the LEP should continue to lobby for the scheme to be delivered at the earliest opportunity and ideally in advance of 2017.

# Text boxes

Scheme Description

The Blackburn to Manchester Rail Corridor Improvements Scheme will deliver a half-hourly service between Blackburn and Manchester throughout the day through the addition of 7 journeys between these stations each day Monday – Saturday. This increased service level will cater for the current demand and improve the economic relationship between East Lancashire and Greater Manchester.

In order to deliver a robust half hourly service throughout the day an extension to the passing loop (double track) at Darwen is required. The project, as identified by Network Rail as the preferred solution through the GRIP process, is to extend the double track section known as the Darwen loop on the Bolton to Blackburn Line, with associated works at structures along that part of the route. In addition, the scheme includes enhancement works at selected stations on the line (including stations north of Blackburn).