**Boost – Lancashire Business Growth Hub – Lead Andrew Leeming**

***BACKGROUND***

Boost (Lancashire's Business Growth Hub) is a multi-tier, multi-agency programme, established in 2013. The programme is funded by the Ministry for Housing, Communities and Local Government (MHCLG), Department for Business, Energy and Industrial Strategy (BEIS) and Lancashire County Council. By 2018 Boost had engaged with over 5,800 businesses, created 2,200 new jobs and generated over £60m GVA for the Lancashire economy. The main focus of Boost 1 (2013-15) and Boost 2 (2016-18) was improving the competitiveness of high growth Lancashire businesses, job creation and helping to establish sustainable new enterprises within Lancashire.

Boost 3 has a total project value of **£6.083m** (£3.650m ESIF (60%) & £2.433m public match) to be defrayed from 1st January 2019 to 30th December 2021.

In addition, c. **£328k** of BEIS funding per annum is used to provide sector specific support and assist beneficiaries who do not fit ERDF eligibility criteria.

Our #BoostYourRecovery campaign was launched in June 2020 to help Lancashire enterprises reset and plan their return from lockdown. Our #AskForHelp campaign, launched on day one of the lockdown has already assisted more than 5000 Lancashire businesses.

Boost has started delivering **Peer Networks programme** for Lancashire. Peer Networks is a national peer-to-peer networking programme for SME leaders that want to grow and develop their organisation for future success. Delivered locally by Boost, we are creating diverse -cohort groups of individuals to collaboratively work through common business issues.

Peer Networks is funded by the Department for Business, Energy and Industrial Strategy (BEIS) in response to a commitment made in the 2019 Business Productivity Review. The programme includes interactive action learning, trained facilitators, small groups, flexible topic selection and one to one coaching.

By completing Peer Networks, an enterprise will overcome business challenges and recognise and act on new opportunities, build a trusted network of connections for immediate support as well as for the future, and improve their long-term personal and business performance.

The new **Boost your recovery Covid grant** funds has received in excess of 1000 expressions of interest, totally over £3M of grant ask. The team have been assessing the returns, its looks like around 70% of theses will be eligible to apply for a grant.

***PERFORMANCE***

The project directly supports **Priority Axis 3** – ‘Enhancing the Competitiveness of small and medium sized enterprises’. Boost specifically addresses the following Investment Priorities:

**3a Promoting entrepreneurship**, in particular by facilitating the economic exploitation of new ideas and fostering the creation of new firms.

**The Growth Support** Programme strand of Boost 3 is specifically designed to identify entrepreneurs who have business ideas with growth potential and to help them bring these to fruition. It provides customised support to equip new businesses with the skills, techniques and tools to understand the barriers to growth and help them to overcome these.

**3c Supporting the creation and the extension of advanced capacities for products, services and development.**

The newly introduced **Business Resilience Programme** together with the **Growth Mentoring Programme** encourages businesses to bring forward growth projects, products and services through ongoing support to develop commercial capabilities and growth strategies.

**3d Supporting the capacity of small and medium sized enterprises to grow in regional, national and international markets and to engage in innovation processes.**

**The Business Resilience Programme** assists existing businesses to examine and develop existing and potential markets at home and abroad. Working alongside the Department for International Trade and local Chambers of Commerce, the initiative helps them to evaluate the threats and opportunities posed by changes in international trade patterns and tariffs and to take action to grow their businesses.

In addition to delivering the specific ERDF related outputs identified, Boost 3 will result in:

* Increased business formation rates
* Improved business survival rates
* An increase in the number of scale up businesses in Lancashire
* Improved productivity and GVA
* Higher levels of innovation and growth
* Business diversification, new products and services
* Higher levels of international trade

**Programme Milestones**

|  |  |  |
| --- | --- | --- |
| **Milestone** | **Start Date** | **Completion Date** |
| LCC Cabinet Approval for match funding | July 2018 | September 2018 |
| Boost 3 Procurement | July – December 2018 | January 2019 |
| Boost 3 Core Delivery Commences | January 2019 | December 2021 |
| Project Delivery (Business Support) | January 2019 | September 2021 |
| Mid Term Evaluation\* | March 2020 | July 2020 |
| Final Evaluation | October 2021 | December 2021 |

\* The mid programme review has been shared with key stake holders and delivery organisations.

**Key Performance Indicators - as at 31st December 2020\***

Boost 1 and 2 programmes are fully complete and closed having achieved the targets.

***In terms of performance for the combined Boost 1, 2 and 3 programmes which contribute to the core LEP KPIs, these are as follows:***

* Combined C8 (**Jobs Created**) = **Actual 3507.57 / Target 3,330.71**
* Combined C1 (number of **enterprises assisted)** = **Actual 3811 / Target 3945.**

The table below contains current core Boost 3 outputs & outcomes as specified in contracts with service providers and GFAs signed with Managing Authorities (MHCLG & BEIS).

BOOST 3

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **KPI** | **Target** | **Achieved** | **Comments** | **RAG** |
| New to Boost (NTB) businesses. | 12501 | **3,913** | 313% of our overall programme target1 has been achieved. 84.17% of Diagnosis of Need were 'New to Boost'. |  |
| (P13) Number of enterprises receiving information, diagnostic and brokerage support. | 980 | **978**  99.79% | The project has superseded its overall target2 by **195.6%.** |  |
| (C5) Number of new enterprises supported. | 175 | **148**  84.57% | C5 is one of the primary indicators for MHCLG\*. We have a satisfactory pipeline, and confident of achieving our pre-Covid-19 contractual targets for this indicator. |  |
| Boost referrals to wider business support agencies. | Target achieved | **2,462** |  |  |
| (P11) Number of potential entrepreneurs assisted to be enterprise ready. | 320 | **254**  79.37% | There is a marked improvement in confidence amongst potential Lancashire entrepreneurs to set up their own businesses during quarter 4, 2020. There is a heathy pipeline of beneficiaries for Q1, 2021. Like other programmes, the start-up programme is working to pre Covid-19 targets. |  |
| (C1) Number of enterprises receiving support (12 Hours or more). \*\* | 950\* | **664**  69.89% | Mentoring Service underperformance coupled with the fact that both service providers and businesses are taking a longer period to complete 12-hour business assist has resulted in lesser C1 completions in Q4. In spite of additional activity, 'immediate' needs are taking priority over 'long term goals' for some businesses and thus resulting in bursts of shorter interventions.  With the added flexibility regarding the categories of businesses that service providers can now engage with, (whilst maintaining ERDF eligibility requirements) we are hoping that some of the shortfall in C1 outputs can be addressed by September 2021. This is subject to market constraints due to Covid-19. Ongoing discussions are taking place with service providers so that 'new solutions' are provided to combat 'new problems' faced by Lancashire businesses. |  |
| (C8) Employment increase in supported enterprises. | 650 | 726.57 111.78% | The programme continues to be ahead of its C8 output target. |  |
| (C28) Number of enterprises supported to introduce new to the market products. | 30 | 06  20% | This is one of the most complex and difficult output for ERDF programmes.  We have asked MA if our C28 shortfall can be replaced by a combination of surplus C5, C8, P13 and P11 outputs. |  |
| (C29) Number of enterprises supported to introduce new to the firm products. | 40 | 12  30% | We have asked MA if our C29 shortfall can be replaced by a combination of surplus C5, C8, P13 and P11 outputs. This is one of the most complex and difficult output for ERDF programmes.  Core service providers are collaborating with other business support agencies. |  |
| Unique website visits | 9,984 | 10,797  108.14% |  |  |
| GDPR Compliant database growth | 1,500 | 3664 |  |  |
| Grow Twitter community | 1,666 | 1,742  104.56% |  |  |
| 4 Subject / Thematic campaigns per annum. | 6 | 6  100% |  |  |

1Identify, engage and support **1250** new to Boost Lancashire businesses

2Programme target for Business Relationship Management Service is **500** BSRs.

**Financial Performance**

This section covers project performance in terms of actual expenditure against the profiled values contained in the Funding Agreement.

* The amount of Eligible Expenditure Defrayed within the claim period is **£510,539.98**
* The financial profile for this period was **£552,222**
* Total cumulative expenditure to date is **£3,833,750** compared to approved profile of

**£3,986,870**

**Note - Boost is working to pre Covid-19 targets with regards to job and wealth creation in the midst of an unprecedented economic crisis.**

***RISKS***

A Single Portfolio Risk Register for the combined programmes is attached to the main report.